## Timeline
Te Tahua Āki Auahatanga ¦ Cultural Sector Innovation Fund
Indicative timeline to 30 June 2021
|  | FY20/21 | [114 empty] | FY21/22
|  | March | [23 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July
| Week | 08/03 - 14/03 | [6 empty] | 15/03 - 21/03 | [6 empty] | 22/03 - 28/03 | [6 empty] | 29/03 - 04/04 | [6 empty] | 05/04 - 11/04 | [6 empty] | 12/04 - 18/04 | [6 empty] | 19/04 - 25/04 | [6 empty] | 26/04 - 02/05 | [6 empty] | 03/05 - 09/05 | [6 empty] | 10/05 - 16/05 | [6 empty] | 17/05 - 23/05 | [6 empty] | 24/05 - 30/05 | [6 empty] | 31/05 - 06/06 | [6 empty] | 07/06 - 13/06 | [6 empty] | 14/06 - 20/06 | [6 empty] | 21/06 - 27/06 | [6 empty] | 28/06 - 04/07
Governance | Planned date | time axis 2021-03-08 to 2021-07-04
Implementation Plan approval | 2021-03-09 | bar: 2021-03-09; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-26; 2021-06-02; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Go / No-Go activities and approval by Jeff/Anna | 25/03 & as needed | bar: 2021-03-22 to 2021-03-26; 2021-04-06; 2021-04-23; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-26; 2021-06-02; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Dashboard / update to SSGC | Weekly ongoing | [119 empty] | ► | bar: 2021-04-13; 2021-04-20; 2021-04-28; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-11 to 2021-05-12; 2021-05-18; 2021-05-25 to 2021-05-26; 2021-06-01 to 2021-06-02; 2021-06-09 to 2021-06-11; 2021-06-14 to 2021-06-16; 2021-06-22; 2021-06-25; 2021-06-29 to 2021-07-01
Panel recommendations considered by SSGC | After each event | 2021-05-10: Consider Panel recommendations; 2021-05-11: ▲; 2021-06-08: Consider Panel recommendations; 2021-06-09: ▲
Procurement Plan for next events and SSGC sign-off | Late May | 2021-05-31: Procurement Plan for next events; 2021-06-01: ▲
Refine design for remaining events & procurement | Mid May | 2021-05-31: Aprove refined design; 2021-06-01: ▲
Seed funding due-diligence, contracting, SSGC sign-off | Mid May - ongoing | 2021-05-24: Seed funding approvals; 2021-05-25: ▲; 2021-06-01: ▲; 2021-06-09: ▲; 2021-06-15: ▲; 2021-06-22: ▲; 2021-06-29: ▲ | ►
Full funding due-diligence, negotiation, SSGC sign-off | Mid May - ongoing | 2021-05-24: Full funding approvals; 2021-05-25: ▲; 2021-06-01: ▲; 2021-06-09: ▲; 2021-06-15: ▲; 2021-06-22: ▲; 2021-06-29: ▲ | ►
Key dates | Planned date | time axis 2021-03-08 to 2021-07-04
Minister announcement and media release | 2021-03-30 | [120 empty] | ▲ | ▲ | ▲ | ▲ | ▲ | bar: 2021-03-30; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12 to 2021-05-14; 2021-06-02; 2021-06-08; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16 to 2021-06-18; 2021-06-21; 2021-06-23 to 2021-06-25; 2021-06-30 to 2021-07-01
Registrations open | 2021-04-09 | 2021-04-08: Registrations open; 2021-04-09: ▲
Cultural Sector Challenge Events - Regional | 30/04 - ongoing | 2021-04-29: Wellington; 2021-05-27: Christchurch; 2021-06-24: Dunedin | ►
Cultural Sector Challenge Events - Online | 12/05 & 26/05 | 2021-05-11: Online workshop; 2021-05-25: Online pitch session
|  | FY20/21 | [114 empty] | FY21/22
|  | March | [23 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July
| Week | 2021-03-08: 08/03 - 14/03; 2021-03-15: 15/03 - 21/03; 2021-03-22: 22/03 - 28/03; 2021-03-29: 29/03 - 04/04; 2021-04-05: 05/04 - 11/04; 2021-04-12: 12/04 - 18/04; 2021-04-19: 19/04 - 25/04; 2021-04-26: 26/04 - 02/05; 2021-05-03: 03/05 - 09/05; 2021-05-10: 10/05 - 16/05; 2021-05-17: 17/05 - 23/05; 2021-05-24: 24/05 - 30/05; 2021-05-31: 31/05 - 06/06; 2021-06-07: 07/06 - 13/06; 2021-06-14: 14/06 - 20/06; 2021-06-21: 21/06 - 27/06; 2021-06-28: 28/06 - 04/07
Stakeholder engagement | Planned date | time axis 2021-03-08 to 2021-07-04
Develop activation packs and collateral | 08/03 - 26/03 | bar: 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-24; 2021-05-26; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Update to sector / Māori design group | 2021-03-29 | bar: 2021-03-29; 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-24; 2021-05-26; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Develop and deliver online information sessions | 22/03 - ongoing | bar: 2021-04-06 to 2021-04-07; 2021-05-03 to 2021-05-05; 2021-05-12; 2021-05-19 to 2021-05-20; 2021-05-24; 2021-05-26; 2021-06-10 to 2021-06-11; 2021-06-14 to 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Regional stakeholder activation | 2021-03-29 | bar: 2021-03-29; 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-24; 2021-05-26; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Iwi engagement activation | 2021-03-29 | bar: 2021-03-29; 2021-05-04 to 2021-05-05; 2021-05-12; 2021-05-24; 2021-05-26; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16; 2021-06-25; 2021-06-30 to 2021-07-01
Engage sector / Māori design group for next events / rounds | Early May | 2021-05-03: Engage sector co-design team; 2021-05-04: ▲
Ongoing sector engagement activities | Ongoing | [119 empty] | ►
Comms & marketing | Planned date | time axis 2021-03-08 to 2021-07-04
Select and brief design agency for visual identity | 08/03 - 12/03
Sign off creative concepts for visual identity | 2021-03-25 | bar: 2021-03-25
Select and brief photographers and videographers | 12/03 - 16/03
Produce collateral | 15/03 - 26/03
Apply look and feel to website and events | 15/03 - 19/03
Minister announcement and media release | 2021-03-30 | bar: 2021-03-30
Marketing and communication campaign activation | 2021-03-30 | bar: 2021-03-30
Ongoing communications activities per event | 30/03 - ongoing | [119 empty] | ► | bar: 2021-03-30 to 2021-04-01
Design | Planned date | time axis 2021-03-08 to 2021-07-04
Develop evaluation criteria and approval | 08/03 - 16/03 | bar: 2021-04-06; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12 to 2021-05-14; 2021-05-24 to 2021-05-27; 2021-06-02; 2021-06-08; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16 to 2021-06-18; 2021-06-21; 2021-06-23 to 2021-06-25; 2021-06-30 to 2021-07-01
Event-management tool approval | 2021-03-19 | bar: 2021-03-19; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12 to 2021-05-14; 2021-05-24 to 2021-05-27; 2021-06-02; 2021-06-08; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16 to 2021-06-18; 2021-06-21; 2021-06-23 to 2021-06-25; 2021-06-30 to 2021-07-01
Event logistics (led by CHQ) | 08/03 - ongoing | bar: 2021-06-28 to 2021-07-01
Configure event-management tool | 15/03 - 19/03 | bar: 2021-03-25 to 2021-03-26; 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12 to 2021-05-14; 2021-05-24 to 2021-05-27; 2021-06-02; 2021-06-08; 2021-06-10 to 2021-06-11; 2021-06-14; 2021-06-16 to 2021-06-18; 2021-06-21; 2021-06-23 to 2021-06-25; 2021-06-30 to 2021-07-01
Review of first two events | Mid May | 2021-05-19: Review sessions
Refine design for remaining events & procurement | Mid May | 2021-05-23: Refine design; 2021-06-01: ▲
Onboarding to Grant Management System | Mid May | 2021-04-20: Grant Management System activities; 2021-05-11: ▲
Scoping / requirements for Innovation Portal / Platform | June | bar: 2021-04-30; 2021-05-04 to 2021-05-05; 2021-05-12 to 2021-05-14; 2021-05-24 to 2021-05-27; 2021-06-02
Procurement | Planned date | time axis 2021-03-08 to 2021-07-04
Procurement Plan for next events and SSGC sign-off | Late May | 2021-05-23: Procurement plan; 2021-06-01: ▲
Procurement activities for event facilitation services | Late May | 2021-06-01: Procurement activities
Implementation | Planned date | time axis 2021-03-08 to 2021-07-04
Registrations open | 2021-04-09 | 2021-04-09: Registrations open; 2021-04-10: ▲
Manatū Taonga Facilitator Training (delivered by CHQ) | 15/04 - 16/04 | 2021-04-14: Facilitator training
Cultural Sector Challenge Events - Regional | 30/04 - ongoing | 2021-04-29: Wellington; 2021-05-27: Christchurch; 2021-06-24: Dunedin | ►
Cultural Sector Challenge Events - Online | 12/05 & 26/05 | 2021-05-11: Online workshop; 2021-05-25: Online pitch session
Performance evaluation and reporting (with PMO) | After each event | 2021-05-03: Reporting; 2021-05-31: Reporting; 2021-06-28: Reporting | ►
Funding | Planned date | time axis 2021-03-08 to 2021-07-04
Panel evaluation and moderation | After each event | 2021-05-03: Panel evaluation; 2021-05-31: Panel evaluation; 2021-06-29: Panel evaluation
Panel recommendations considered by SSGC | After each event | 2021-05-10: Panel recommendations considered; 2021-05-11: ▲; 2021-06-08: Panel recommendations considered; 2021-06-09: ▲
Seed funding due-diligence, contracting, SSGC sign-off | Mid May - ongoing | 2021-05-11: Seed funding contracting; 2021-05-25: ▲; 2021-06-01: ▲; 2021-06-09: ▲; 2021-06-15: ▲; 2021-06-22: ▲; 2021-06-29: ▲ | ►
Full funding due-diligence, negotiation, SSGC sign-off | Mid May - ongoing | 2021-05-11: Full funding contracting; 2021-05-25: ▲; 2021-06-01: ▲; 2021-06-09: ▲; 2021-06-15: ▲; 2021-06-22: ▲; 2021-06-29: ▲ | ►
COVID Response Programme Initiatives | Planned date | time axis 2021-03-08 to 2021-07-04
CARE Creative Spaces Funding R1 applications open | Open - 24/03 | bar: 2021-03-08 to 2021-03-24
Grant Management System client-portal launched | 2021-04-07 | bar: 2021-04-07
CARE Cultural Installations R1 applications open | 07/04 - 05/05 | bar: 2021-04-07 to 2021-05-05
CARE Cultural Activators Pilot | 28/04 - 26/05 | bar: 2021-04-28 to 2021-05-26
CARE Creative Spaces Funding R2 applications open | 04/05 - 01/05 | bar: 2021-05-04 to 2021-06-01
Capability Fund R2 | 08/06 - 02/07 | bar: 2021-06-08 to 2021-07-02

## High-level timeline
Te Urungi Event High-level workflow
| Weeks before event | [13 empty] | Weeks after the event
Design | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 | Event | 1 |  | 2 | 3 |  | 4
Fund design / refinements
Post-event lessons learned, refinement
Stakeholder engagement | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 |  | 1 |  | 2 | 3 |  | 4
Strategic stakeholder engagement
Mana whenua engagement
Post-event engagement, thanks, etc.
Add/manage event participants in CRM | [20 empty] | ►
Comms & marketing | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 |  | 1 |  | 2 | 3 |  | 4
Prepare comms & marketing for launch
Launch | [7 empty] | ▲
Pre-event briefings
Post-event comms / survey / waitlist follow-up
Event management | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 |  | 1 |  | 2 | 3 |  | 4
Event design, logistics, and administration
Confirm experts / mentors availability, conflicts, and contracts
Finalise run sheet | [9 empty] | ▲
Event stationery, collateral, equipment, printing, etc.
Registration management | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 |  | 1 |  | 2 | 3 |  | 4
Configure and test EventBrite
Registrations open | [9 empty] | ▲
Manage exceptions to terms & conditions
Contact participants with accessibility requirements
Demographic analysis
Manage waitlist / release registrations
Confirm final participant list | [11 empty] | ▲
Confirm actual event attendance
Investments & Outcomes | -12 | -11 | -10 | -9 | -8 | -7 | -6 |  | -5 | -4 | -3 | -2 | -1 |  | 1 |  | 2 | 3 |  | 4
Enquiries management
Confirm Panel availability, conflicts, and contracts
Panel pre-event briefing |  |  |  |  | ▲
Travel arrangements for Manatū Taonga staff and Panel
Plan Panel evaluation sessions
Process applicant supporting documentation
Prepare for Panel meeting
Panel meeting | [15 empty] | ▲
Recommendation Paper to SSGC
Manage applications in CFMS | [20 empty] | ►
SSGC decisions | [18 empty] | ▲
Noting Paper to Minister
Notification of applicants / recipients
Funding agreement negotiation | [20 empty] | ►
Event tasks
- Facilitation
- MC
- Answering Fund specific queries
- Capture actual event attendance vs registrations
- General MCH representative and event support crew
- Collect key information from each team to use for scheduling
- Set up sharepoint folders for each team
- Create copies of team details for panel member use
- Panel room set up
- Develop schedule
- Respond to all general panel needs/requirements
- Set up tech for participants (eg powerpoints)
- Operate timer throughout all meetings (5 mins, 4 mins)
- Operate camcorder through each event
- Move all visual/audio recordings into sharepoint folders
- Ensure security of any hard copy docs and equipment

## Insane timeline
Te Tahua Āki Auahatanga ¦ Cultural Sector Innovation Fund
Indicative timeline to 30 December 2021
Note this timeline does not capture ongoing "BAU" activities, e.g. stakeholder management, contract management, CFMS, CRM, etc.
|  | FY20/21 | [22 empty] | FY21/22
| June | [23 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
| 07/06 - 13/06 | [6 empty] | 14/06 - 20/06 | [6 empty] | 21/06 - 27/06 | [6 empty] | 28/06 - 04/07 | [6 empty] | 05/07 - 11/07 | [6 empty] | 12/07 - 18/07 | [6 empty] | 19/07 - 25/07 | [6 empty] | 26/07 - 01/08 | [6 empty] | 02/08 - 08/08 | [6 empty] | 09/08 - 15/08 | [6 empty] | 16/08 - 22/08 | [6 empty] | 23/08 - 29/08 | [6 empty] | 30/08 - 05/09 | [6 empty] | 06/09 - 12/09 | [6 empty] | 13/09 - 19/09 | [6 empty] | 20/09 - 26/09 | [6 empty] | 27/09 - 03/10 | [6 empty] | 04/10 - 10/10 | [6 empty] | 11/10 - 17/10 | [6 empty] | 18/10 - 24/10 | [6 empty] | 25/10 - 31/10 | [6 empty] | 01/11 - 07/11 | [6 empty] | 08/11 - 14/11 | [6 empty] | 15/11 - 21/11 | [6 empty] | 22/11 - 28/11 | [6 empty] | 29/11 - 05/12 | [6 empty] | 06/12 - 12/12 | [6 empty] | 13/12 - 19/12 | [6 empty] | 20/12 - 26/12 | [6 empty] | 27/12 - 02/01
Design | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02
Post-event lessons learned
Procurement milestones?
Stakeholder engagement | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Strategic stakeholder engagement
Mana whenua engagement
Post-event engagement, thanks, etc. | bar: 1900-02-11 to 1900-02-15
Eco-system milestones?
Comms & marketing | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Prepare comms & marketing for launch event 3
Panel pre-event briefing |  |  | ▲
Pre-event briefing for event 3
Event 3 launch | [22 empty] | ▲
Prepare comms & marketing for launch event 4
Panel pre-event briefing | [31 empty] | ▲
Pre-event briefing for event 4
Event 4 launch | [36 empty] | ▲
Prepare comms & marketing for launch event 5
Pre-event briefing for event 5
Event 5 launch | [50 empty] | ▲
Prepare comms & marketing for launch event 6
Pre-event briefing for event 6
Event 6 launch | [64 empty] | ▲
Prepare comms & marketing for launch event 7
Pre-event briefing for event 7
Event 7 launch | [78 empty] | ▲
Prepare comms & marketing for launch event 8
Pre-event briefing for event 8
Event 8 launch | [92 empty] | ▲
Prepare comms & marketing for launch event 9
Pre-event briefing for event 9
Event 9 launch | [106 empty] | ▲
Prepare comms & marketing for launch event 10
Pre-event briefing for event 10
Event 10 launch | [120 empty] | ▲
Prepare comms & marketing for launch events 11 & 12
Event 7 launch | [134 empty] | ▲
Prepare comms & marketing for launch event 13
▲
Pre-event briefings
Post-event comms, survey, etc. | bar: 1900-02-11 to 1900-02-15
Event management | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Finalise and distribute run sheet
Event design, logistics, and administration
Confirm experts / mentors contracts, conflicts, availability
Event stationery, collateral, printing, etc.
Registration management | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Configure and test EventBrite
Registrations open |  | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲
Manage registrations
Confirm final participant list | [14 empty] | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲
Investments & Outcomes | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Confirm Panel contracts, conflicts, availability | bar: 1900-02-14 to 1900-02-15
Plan Panel evaluation sessions | bar: 1900-02-14 to 1900-02-15
Process applicant supporting documentation | bar: 1900-02-11 to 1900-02-12; 1900-02-14 to 1900-02-15
Prepare for Panel meeting | bar: 1900-02-11 to 1900-02-12; 1900-02-14 to 1900-02-15
Panel meeting | [17 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [5 empty] | ▲ | ▲ | ▲ | [12 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [18 empty] | ▲ | [13 empty] | ▲ | ▲ | ▲ | [5 empty] | ▲ | [13 empty] | ▲ | bar: 1900-02-13 to 1900-02-15
Recommendation Paper to SSGC | bar: 1900-02-14 to 1900-02-15; 1900-02-18 to 1900-02-20
SSGC decisions | [29 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [6 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [6 empty] | ▲ | bar: 1900-02-12; 1900-02-14 to 1900-02-15
Noting Paper to Minister | bar: 1900-02-13 to 1900-02-15
Notification of applicants / recipients | bar: 1900-02-13 to 1900-02-15; 1900-02-18 to 1900-02-19

## Detailed timeline
Te Tahua Āki Auahatanga ¦ Cultural Sector Innovation Fund
Indicative timeline to 30 December 2021
Note this timeline does not capture ongoing "BAU" activities, e.g. stakeholder management, contract management, CFMS, CRM, etc.
|  | FY20/21 | [22 empty] | FY21/22
| June | [23 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
| 07/06 - 13/06 | [6 empty] | 14/06 - 20/06 | [6 empty] | 21/06 - 27/06 | [6 empty] | 28/06 - 04/07 | [6 empty] | 05/07 - 11/07 | [6 empty] | 12/07 - 18/07 | [6 empty] | 19/07 - 25/07 | [6 empty] | 26/07 - 01/08 | [6 empty] | 02/08 - 08/08 | [6 empty] | 09/08 - 15/08 | [6 empty] | 16/08 - 22/08 | [6 empty] | 23/08 - 29/08 | [6 empty] | 30/08 - 05/09 | [6 empty] | 06/09 - 12/09 | [6 empty] | 13/09 - 19/09 | [6 empty] | 20/09 - 26/09 | [6 empty] | 27/09 - 03/10 | [6 empty] | 04/10 - 10/10 | [6 empty] | 11/10 - 17/10 | [6 empty] | 18/10 - 24/10 | [6 empty] | 25/10 - 31/10 | [6 empty] | 01/11 - 07/11 | [6 empty] | 08/11 - 14/11 | [6 empty] | 15/11 - 21/11 | [6 empty] | 22/11 - 28/11 | [6 empty] | 29/11 - 05/12 | [6 empty] | 06/12 - 12/12 | [6 empty] | 13/12 - 19/12 | [6 empty] | 20/12 - 26/12 | [6 empty] | 27/12 - 02/01
Design | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02
Post-event lessons learned
Procurement milestones?
Stakeholder engagement | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Strategic stakeholder engagement | bar: 1900-02-14 to 1900-02-15
Mana whenua engagement | bar: 1900-02-14 to 1900-02-15
Post-event engagement, thanks, etc. | bar: 1900-02-11 to 1900-02-15
Eco-system milestones? | bar: 1900-02-14 to 1900-02-15
Comms & marketing | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Prepare comms & marketing for launch
Event launch | [22 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲
Pre-event briefings
Post-event comms, survey, etc. | bar: 1900-02-11 to 1900-02-15
Event management | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Finalise and distribute run sheet
Event design, logistics, and administration
Confirm experts / mentors contracts, conflicts, availability
Event stationery, collateral, printing, etc.
Registration management | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Configure and test EventBrite
Registrations open |  | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲
Manage registrations
Confirm final participant list | [14 empty] | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲
Investments & Outcomes | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 |  |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 |  |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 |  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 |  |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 |  |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 |  |  |  | 2021-10-18 | 2021-10-19 |  | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 |  |  |  | 1899-12-31 | 1900-01-01 |  | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 |  |  |  | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 |  |  |  | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 |  |  |  | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03
Confirm Panel contracts, conflicts, availability | bar: 1900-02-14 to 1900-02-15
Panel pre-event briefing |  |  | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [14 empty] | ▲ | [13 empty] | ▲ | [12 empty] | ▲ | [13 empty] | ▲ | bar: 1900-02-14 to 1900-02-15
Plan Panel evaluation sessions | bar: 1900-02-14 to 1900-02-15
Process applicant supporting documentation | bar: 1900-02-11 to 1900-02-12; 1900-02-14 to 1900-02-15
Prepare for Panel meeting | bar: 1900-02-11 to 1900-02-12; 1900-02-14 to 1900-02-15
Panel meeting | [17 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [5 empty] | ▲ | ▲ | ▲ | [12 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [18 empty] | ▲ | [13 empty] | ▲ | ▲ | ▲ | [5 empty] | ▲ | [13 empty] | ▲ | bar: 1900-02-13 to 1900-02-15
Recommendation Paper to SSGC | bar: 1900-02-14 to 1900-02-15; 1900-02-18 to 1900-02-20
SSGC decisions | [29 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [6 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [13 empty] | ▲ | [20 empty] | ▲ | [13 empty] | ▲ | [6 empty] | ▲ | bar: 1900-02-12; 1900-02-14 to 1900-02-15
Noting Paper to Minister | bar: 1900-02-13 to 1900-02-15
Notification of applicants / recipients | bar: 1900-02-13 to 1900-02-15; 1900-02-18 to 1900-02-19

## Comms Plan
Cultural Sector Challenge Events
Communications and engagement phasing
[15 empty] | FY20/21 | FY21/22
| March |  |  |  | April |  |  |  | May |  |  |  | June |  |  | July
National awareness campaign | National awareness campaign
Te Whanganui-a-Tara |  | Pre-engagement | Regional event promotion and engagement |  | Registrations open |  |  | Event | Post-event communications and engagement (ongoing)
Promotion and engagement cont'd
Online event |  |  |  | Pre-engagement | Regional event promotion and engagement |  | Registrations open |  |  | Event | Post-event communications and engagement (ongoing)
Promotion and engagement cont'd
Ōtautahi | [5 empty] | Pre-engagement | Regional event promotion and engagement |  | Registrations open |  |  | Event | Post-event communications and engagement (ongoing)
Promotion and engagement cont'd
Ōtepoti | [9 empty] | Pre-engagement | Regional event promotion and engagement |  | Registrations open |  | Event | Post-event communications and engagement (ongoing)
Promotion and engagement cont'd
|  | Future events TBC | [9 empty] | Pre-engagement | Regional event promotion and engagement | Registrations open |  |  | Event | Post-event communications and engagement( ongoing)
Promotion and engagement cont'd

## Sheet1
▲ | ▲ | ▲ | ▲ | ▲