## SiD Register
Hazard ID | Hutt CC | Zone | Discipline | Hazard Occurrence | Source | Hazard Description | Potential Cause | Potential Consequence | Initial Consequence | ICQLVL | Initial Likelihood | ILLHLVL | InitialRiskN%23 | Initial Risk Rating | Design Lead / Owner | Controls/Mitigations to Incorporate in Design | Post Design Control Consequence | Post Design Control Likelihood | Post Design Control Risk Rating | Status | Construction Controls | Residual Construction Consequence | Residual Construction Likelihood | Residual Construction Risk Rating | Operation and Maintenance Controls | Residual O&M Consequence | Residual O&M Likelihood | Residual O&M Risk Rating | Font
1 | Y | Project Wide | General | Construction | TAN-0066 / TAN-0100 | Interfaces of the construction work with members of the public. e.g. How does this interface with walkways along waterfront - close / divert walkways / construction fencing. urban intersections - full closures to remove risk from traffic to worksite | Member of the public able to access site (even if lockable hatches / doors provided) | Accident / injury / death to member of public accessing construction site | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Fairweather Is Matt part of the design team, or should he be the contractor that the SiD is handed on to? | Design in viewing areas. Permanent fencing rather than temporary. Shut down certain areas Liaise with construction team to ensure design allows for sufficient space for adequate temporary facilities for vulnerable users including pedestrians and cyclists. Evaluate road detour options including provision of sufficient capacity etc. Design for temporary works to meet minimum criteria (e.g. 30km/h for temporary roads). 15/04/25 - construction team to lead with design support | Extreme | Possible | Critical | Construction | Ensure good practice controls implemented. E.g. CCNZ Practice Note: Protecting Vulnerable Road Users in TTM environments and CHASNZ Temporary Works Procedural Control |  |  | Unknown |  |  |  | Unknown
2 | Y | Project Wide | General | Construction | TAN-0066 | Crime due to lack of monitoring | No provision of security cameras to monitor construction site | Accident or injury / damage to construction site | Minor | 1 | Possible | 2 | 2 | Medium | Matt Fairweather | MRs require that temporary CCTV is installed for the project 15/04/25 - construction team to lead with design support | Minor | Unlikely | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
3 | Y | Project Wide | General | Construction | TAN-0101 / TAN-106 | Lifting heavy construction elements | Strong winds, unstable load, incorrect lifting arrangement or procedure. | Accident / injury / death from lifting heavy elements or due to heavy elements falling when lifted. Damage to plant or assets. | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Matt Fairweather | Review different bridge forms that are lighter - consider lighter sections might be more at risk in wind. Consider sections to be lifted in throughout the design. and make them as efficient as possible in terms of centre of gravity and size, weight and shape Design in lifting points where possible. Lifting points review for maintenance activities - ease of addition of maintenance scaffold to access bridge Understand lifting capacities of readily available cranes, their required operating area (include swing area) and take into consideration when completing design. Ensure constructors have strong protocols in place for when wind conditions exceed capabilities to control. 15/04/25 - design has/will take into account these considerations in conjunction with construction team. construction team to lead with design support | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
4 |  | Project Wide | General | Construction | workshop 8/08/23 | Confined spaces | Excavations, manholes, | Accident / injury / death due to collapse of confined space or suffocation is collapse part of this????? | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | Reduce the scope of drainage where possible and try and keep existing access. Reduce number of MHs where possible. For smaller manholes consider specifying pre haunched manholes? Consider providing access ladders in manholes. Ensure manholes and other confined spaces have an appropriate area available at ground level to allow &#39;lifting apparatus&#39; to be placed to lower/lift individuals in/out of confined spaces (in emergency situation). Include operational risk and mitigation measures in O&amp;M manuals 15/04/25 - design has/will take into account these considerations in conjunction with construction team. construction team to lead with design support | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
5 |  | Project Wide | General | Construction | TAN-0126 / TAN-0106 | Working in and around live traffic | Traffic hazards on live roads. The need for personnel and plant to work adjacent to an active carriageway. Optimisation of &quot;permanent&quot; space limits room for construction space. | Risk of errant vehicle strike with associated harm or equipment damage. Congestion of network especially around peak periods, increased frustration leading to traffic accidents. | Extreme | 4 | Likely | 3 | 4 | Critical | Travis Medhurst | Temporary Road Safety Barrier Designs will be completed by the Higgins TTM Team. TRSB&#39;s will be installed on Long Term Project Sites and Risk Assessed for all sites taking into account all road users and workers safety. Hierarchy of Controls TTM approach to TTM/Construction methodology will be adopted i.e. Road Closures - One Way Detours - Stop Go Liaise with construction team to ensure design provides space and alignment to provide TTM with adequate capacity and alignment to minimise risk of road user frustration. 15/04/25 - construction team to lead with design support | Extreme | Possible | Critical | Construction | Ensure most vulnerable road users (e.g. cyclists and pedestrians) are adequately included in all TTM Ensure emergency services are included in TTM development, emergency services routes identified and priority given to these to ensure risk of disruption is minimised. Construction programme and methodology to be developed in a manner that provides adequate provisions |  |  | Unknown |  |  |  | Unknown
6 |  | Project Wide | General | Construction | TAN-0126 / TAN-0106 | Working in and around live traffic | Optimisation of "permanent" space limits room for construction space. | Risk of errant vehicle strike with associated harm or equipment damage. Congestion of network especially around peak periods, increased frustration leading to traffic accidents. | Extreme | 4 | Likely | 3 | 4 | Critical | Travis Medhurst | Design and review staging plans to ensure adequate safe work space has been allowed. Ensure there is onsite assistance for TTM emergency response to ensure traffic flow is maintained and disruption is kept to a minimum. Clear precise safe speeds through work sites Clear precise installation of TTM devices and Line marking for road users to minimise road user confusion &amp; frustration 15/04/25 - construction team to lead with design support | Severe | Possible | High | Construction | Ensure emergency services are included in TTM development, emergency services routes identified and priority given to these to ensure risk of disruption is minimised. Identify &#39;Plan B&#39; options that can be quickly implemented to allow traffic flow to recommence (e.g. tow vehicle on site, alternative route that can b Construction programme and methodology to be developed in a manner that provides adequate provisions opened quickly, shoulders that can be used for traffic, etc.). |  |  | Unknown |  |  |  | Unknown
7 |  | Project Wide | General | Construction | workshop 8/08/23 | Earthquake risk during construction | Earthquake occurs during construction | Accident / injury / death due to debris from damaged infrastructure | Extreme | 4 | Possible | 2 | 4 | Critical | Gareth Hole | Temporary works designed by ENZ CPEng to requirements of NZS1170. Ensure that permanent works designers understand proposed construction methods / staging so that any reliance upon previously constructed permanent works (e.g. pier stems) can be accounted for in permanent works design load cases Provide sufficient space for escape routes and assembly points to be provided. This includes both egress for workers and access for emergency services. 15/04/25 - construction team to lead with design support | Extreme | Rare | High | Construction | Provide sufficient space for escape routes and assembly points to be provided. This includes both egress for workers and access for emergency services. |  |  | Unknown |  |  |  | Unknown
8 |  | Project Wide | General | Construction | TAN-0128 | Nightworks | Nightworks required during construction | Extra over risk of Injury / death due to accident resulting from fatigue | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | Drainage across SH2 are the current areas that will need night works. Try to use existing crossing if possible. Due to impact on traffic flows, likely that it will become desirable for other activities such as surfacing, road markings and movement of TTM major works to be undertaken at night. Ensure adequate space is available for measures such as lighting, additional TTM and site facilities for night work. 15/04/25 - construction team to lead with design support | Severe | Unlikely | Medium | Construction | Construction team to deploy appropriate controls and measures to minimise risk including fatigue. |  |  | Unknown |  |  |  | Unknown
9 | Y | Project Wide | General | Construction | TAN-0128 | Harm to residents in properties adjacent to works area | Limited access to property during construction | Accident / injury to residents trying to access property | Moderate | 2 | Possible | 2 | 2 | Medium | Matt Fairweather | Set a standard Temporary Vehicle access Temporary Design prior to construction. High Med & Low Standard Design to cater to each environment. Comms to engage early for overnight or longer Vehicle access closures. Exclusion zones established to separate public and work zones 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
10 |  | Project Wide | General | Construction | TAN-0122 | Working below the water table | High water table when working at depth / with deep excavations | Accident / injury / death due to unexpected water ingress into excavation | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Simon Fulford | Detailed design may include Geotechnical Assessment at or below water table level and may result in the need to consider alternate construction solutions. If sheet piles are to be utilised for a trenching solution below the water table industry standard practice would be to design a dewatering system to cope with expected inflow volumes that draws the water table down below the trench subgrade. Any pump or dewatering system failure would normally result in a gradual rise in the water table not sufficient to cause sudden inundation of the excavation. Ensure emergency lifting apparatus is available for all subsurface investigations to allow individual(s) to be removed quickly, if required 15/04/25 - detailed incorporates above. Construction team to lead with design support | Severe | Rare | Low | Construction | If sheet piles are to be utilised for a trenching solution below the water table industry standard practice would be to design a dewatering system to cope with expected inflow volumes that draws the water table down below the trench subgrade. Any pump or dewatering system failure would normally result in a gradual rise in the water table not sufficient to cause sudden inundation of the excavation. |  |  | Unknown |  |  |  | Unknown
011a | Y | Project Wide | General | Design | GHD SiD Register - 59 | Contact with contaminated land | Contact with contaminated material - e.g. asbestos during building demolition, unknown material within stopbanks, works in HAIL sites, rail corridor, relocation of train station building | Illness / death | Extreme | 4 | Possible | 2 | 4 | Critical | Shane Soulsby | Use available technical report #13 and GWRC SLUR register to minimise design elements &amp; change of ground level in medium/high risk areas where possible. Utilise gas monitors and masks whenever contamination concern is identified. Test all building materials that have the potential to contain asbestos to allow early identification. 15/04/25 - contamination identified in rail ballast, options being considered. see 011b 06/25 - HCC, recommend included in project contamination management plan 06/08/2025 PC - Contaminated material retained within the site is to be recorded & sites captured in registers to be provided in a contamination management plan as noted above | Extreme | Unlikely | High | Open - Managed | Work in areas of contamination or Asbestos to only be undertaken by trained specialists experienced in this type of work |  |  | Unknown |  |  |  | Unknown
12 | Y | Project Wide | General | Construction | GHD SiD Register - 50 | Emergency vehicle / life line route / heavy haulage access through the site during construction | Traffic management | Delayed emergency response. Traffic accident | Severe | 3 | Possible | 2 | 3 | High | Travis Medhurst | Design and review staging plans to ensure adequate safe travel space for all road users and especially OD/Heavy Haulage. Create and share via comms/ Stakeholder teams to FENZ/Heavy Haulage a VMP (Vehicle Movement Plan) i.e. Site Access Points etc should there be an incident onsite requiring Emergency Services assistance. Keep updated and shared as sites change. 15/04/25 - construction team to lead with design support | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
13 | Y | Project Wide | General | Construction | GHD SiD Register - 43 | Poorly managed interface between multiple construction sites | Interaction with adjacent contractors - i.e. around the service lane, Knights Road cycleway project, Alliance, GWRC, HCC works | Accident / injury | Moderate | 2 | Possible | 2 | 2 | Medium | Matt Fairweather | This is a risk to be controlled in construction. NZTA network activity planning. Use principal to develop process for co-ordination with local road works. 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
14 | Y | Project Wide | General | Construction | GHD SiD Register - 15 | Construction around live traffic | Retaining wall construction above live SH2 | Traffic accident. | Extreme | 4 | Likely | 3 | 4 | Critical | Travis Medhurst | Liaise with construction team to ensure design provides sufficient space for task specific TTM etc. 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction | Distraction and clutter to road users should be minimised when and where possible. Example - Off Site/Out of Site fabrication. Large scale lifts with potential for distraction or falling objects within road corridors should e completed under lane closures or full Closures. Use gawk Screens on Barriers |  |  | Unknown |  |  |  | Unknown
15 | Y | Project Wide | General | Construction | GHD SiD Register - 58 | Material transportation | Transportation of large materials (bridge beams etc...) | Delays/traffic disruptions. Loss of reputation. | Moderate | 2 | Likely | 3 | 3 | High | Gareth Hole | Preference for design solutions that provide flexibility wrt module dimensions / weight etc where pushing envelope during IPAA stage (i.e., once constraints are better understood at PAA stage, long steel girders can be more readily spliced onsite (if required) when contrast with long precast girders). 15/04/25 - construction team to lead with design support | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
16 | Y | Project Wide | General | Construction | GHD SiD Register - 37 | Dangerous parking practices during construction | Unsafe user behaviour | Injury due to traffic accident. | Moderate | 2 | Likely | 3 | 3 | High | Travis Medhurst | Circulate VMP (Vehicle Movement Plan) to wider group and regularly update and share. Transitional parking plan - plan for moving park and ride demand to alternate station(s) (Western Hutt/ Waterloo) and receiving station capacity for additional traffic. 15/04/25 - construction team to lead with design support | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
17 | Y | Project Wide | General | Construction | GHD SiD Register - 56 | Poor cyclist / pedestrian provision across site (e.g. Haul Roads) | Poor cyclist / pedestrian provision | Accident / Injury | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Travis Medhurst | Set a standard pedestrian &amp; Cyclist Temporary Design prior to construction. High Med &amp; Low Standard Design to cater to each environment. Detour peds &amp; cyclists when possible. Exclude or close shared paths as potential mitigation where conflicting with heavy plant operation or key high vehicle traffic location 15/04/25 - construction team to lead with design support | Extreme | Possible | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
18 |  | Project Wide | General | Construction | workshop 8/08/23 GHD SiD Register - 46 | Flood risk to personnel during construction | Flood event occurs while working in / around waterways | Accident / injury / death | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Fairweather | Carry out hydraulic modelling of the river based on construction staging. Develop flood response plan which has TARPs based on flow monitoring 15/04/25 - construction team to lead with design support | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
19 | Y | Project Wide | General | Construction | TGDD SiD Register - 8 | Earth moving machinery | Interaction with services (e.g. power and fibre optic cables), especially large earth moving machinery operating in a confined alignment | Injury or possible death from impact | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Taylor | Close liaison with service authorities to identify all know services. Site investigations/potholing to confirm accuracy of service records (especially HV and fibre). Site inspections to identify signs of any unknown services (e.g. trenches, marker posts etc) Design new services alignment and construction work to avoid high risk areas where practicable Upload existing and proposed services data model to the ‘RevealTwin’, this app to be used by construction team to provide live and up-to-date information, including as-built information. Ensure all appropriate construction team members have app installed and access to data model. 15/04/25 - construction team to lead with design support | Extreme | Possible | Critical | Construction | Excavation permits and protocols. Contractor staging plans to be reviewed to isolate plant from personnel / pedestrian movement. investigate / stipulate the use of digital shielding / machine control to control risk near high impact receivers (KiwiRail T2UH Digital shield as example) |  |  | Unknown |  |  |  | Unknown
20 |  | Project Wide | General | Construction | TGDD SiD Register - 12 | Dust | The hazard of dust covering insulators causing shorts. | Risk of electrocution | Moderate | 2 | Likely | 3 | 3 | High | Mike McConnell | Minimise volume of earthworks allowing completion and stabilisation (reduction in dust generating potential) as quickly as possible. Main risk to be addressed with construction controls. Air quality management plan & control requirements established. air quality monitoring onsite & maintained throughout project 15/04/25 - construction team to lead with design support 06/08/2025 PC - To capture as appropriate in the design. Issue becomes a construction concern for wider areas (residents/local roads/etc.) for protection of Insulators. | Moderate | Unlikely | Medium | Construction | Compliance with various Construction Management Plans and industry best practice |  |  | Unknown |  |  |  | Unknown
21 | Y | Project Wide | General | Construction | TGDD SiD Register - 14 | Muck shift during construction | Mud and dirt spread on road from construction vehicle vehicles | Road accidents on local roads | Moderate | 2 | Possible | 2 | 2 | Medium | Mike McConnell | Minimise volume of earthworks allowing completion and stabilisation (reduction in sediment and mud generating potential) as quickly as possible. Main risk to be addressed with construction controls. Majority imported material - majority of risk moved to established quarry facilities. potential for use of recovered material for bulk fill. 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
22 | Y | Project Wide | General | Construction | SiD workshop 07/09/23 | Rock thrown from dual wheel trucks | Rock stuck between dual wheels on trucks then thrown out the back | Injury/death | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Taylor | Identify specified materials that are at risk of this situation and advise contractor. 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction | Contractor to develop methodology to identify and minimise risk |  |  | Unknown |  |  |  | Unknown
23 | Y | Project Wide | General | Construction | SiD workshop 07/09/23 | Active mode users accessing river works sites | Users of corridor on foot, bike etc. enter river work sites and/or need to move through the corridor | Injury/death from drowning | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Shane Soulsby | None noted as not able to control through design, primarily a construction risk 15/04/25 - construction team to lead with design support | Extreme | Rare | High | Construction | Contractor to minimise site entry/exit locations and to implement controls (e.g. gatemen) to minimise likelihood of situation occurring |  |  | Unknown |  |  |  | Unknown
24 | Y | Project Wide | General | Construction | SiD workshop 07/09/23 | Construction activities visible from road. | Drivers distracted by construction activities. | accident/injury due to collisions. Road closures. | Severe | 3 | Possible | 2 | 3 | High | Travis Medhurst | Distraction and clutter to road users should be minimised when and where possible. Example - Off Site/Out of Site fabrication. Use Gawk Screens on Road Safety Barriers when possible without interfering with site lines for road users. 15/04/25 - construction team to lead with design support | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
25 |  | Project Wide | General | Construction | SiD workshop 07/09/23 | Plant operators not leaving plant in disaster/event. | No clear direction on where to abandon crane, truck etc. | Injury or death of operator trapped in plant. | Extreme | 4 | Unlikely | 1 | 3 | High | Matt Fairweather | Assume this relates to floods. Carry out hydraulic modelling of the river and design / assign safe flood refuge locations 15/04/25 - construction team to lead with design support | Severe | Unlikely | Medium | Construction | Clear instructions for plant operator on what to o in event of flood or earthquake. |  |  | Unknown |  |  |  | Unknown
26 | Y | Project Wide | Site Clearance | Construction | SiD workshop 07/09/23 | Site clearance - exposure to contaminated material, BPC, DTEs, HAIL, siliceous, asbestos, carbons, crushing gravel etc. | Industry, buried, old utilities (for relocation or abandon). | Historic installation as demolition practices | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | Design to minimise processing for crushing. Design to fill over HAIL sites if possible - I.e. not to disturb Design to leave asbestos pipes in place and grout if they are abandoned Undertake testing of any areas of concern to identify early 15/04/25 - design incorporates above where practicable. Construction team to lead with design support | Extreme | Possible | Critical | Construction | Work in areas of risk to be undertaken by trained specialists experienced in this type of work |  |  | Unknown |  |  |  | Unknown
27 |  | West Bank | Site Clearance | Construction | SiD workshop 07/09/23 | Tree felling above SH2 | Trees being removed on steep cliff face or tree that remain falls due to being exposed to wind that was not previously exposed to. | Accident/injury/death | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Fairweather | Design the interchange to move as far East as possible to eliminate the need to fell these trees. If trees need to be felled, design to specify felling to a distance equal to expected growth height from interchange (plus safety margin). Design to consider fencing off any tress that are at risk of falling post construction to minimise risk of public entry 04/25 - design incorporates above as much as practicably possible, transfer balance of risk to construction team | Extreme | Rare | High | Construction | Consider removal via heli. |  |  | Unknown |  |  |  | Unknown
28 |  | Project Wide | General | Construction/ Maintenance | workshop 8/08/23 | Plant roll over | Uneven, unstable or sloping ground | Injury / death. Damage to plant or infrastructure. | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | Consider plant access in design - e.g. when access retaining wall areas for example Remove steep landscape in design - Review of proposed work methodologies and overburden requirements for proper compaction of slopes 04/25 - design incorporates where practicable, transfer to construction team | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
29 | Y | Project Wide | General | Construction/ Maintenance | GHD SiD Register - 47 | Working at heights | Working over the live State Highway - i.e. the interchange bridge and river Personnel, public or maintenance personnel fall from unprotected edge/ retaining wall or fall down steep slope | Traffic accident. Injury/death due to accident. | Extreme | 4 | Possible | 2 | 4 | Critical | Gareth Hole | Design with modularisation in mind. Preference for constructing elevated structures on ground and lifting into position wherever both possible and practical. Preference for bolted connections over welded connections wherever the connection of modules at height is required. Edge protection on embankments, retaining walls, drainage features. use landscaping features (i.e. native bushes or vegetation) to prevent or reduce impact from falls down embankments from cycleways and to prevent &quot;shortcutting&quot; up or across steep or dangerous slopes 04/25 - above incorporated into design where possible | Extreme | Unlikely | High | Construction | Develop methodology and TTM that allows Separation of traffic from workface at all times. |  |  | Unknown |  |  |  | Unknown
30 | Y | Project Wide | General | Construction/ Maintenance | GHD SiD Register - 60 | Unsafe property arrangements | Need to maintain in / out 24/7 access to service lane to rear of properties during construction and after | Accident / injury. Loss of reputation. Disgruntled stakeholders. | Moderate | 2 | Possible | 2 | 2 | Medium | Travis Medhurst | Early comms engagement, Utilisation of Core Flute Signs to identify to customers businesses are still open. Work with businesses to allow customers through road closures etc 15/04/25 - design incorporates above where practicable. Construction team to lead with design support | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
31 | Y | Project Wide | General | Maintenance | GHD SiD Register - 65 | Maintenance access | No safe access to areas requiring maintenance / inspections to be considered. i.e. vegetation areas, abutments | Injury due to slip / trip / fall | Moderate | 2 | Likely | 3 | 3 | High | Matt Fairweather | Design to minimise maintenance requirements Use of steps / handrail Reduce slope and remove trip hazards Provide anchor points 04/25 - ongoing 06/08/2025 PC - Key items to be assessed by wider stakeholders with areas needing access under TM to be managed/balanced with routine maintenance i.e. parking (maintenance bays) vs. lane closures for difference asset owners. Ongoing | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
32 | Y | Project Wide | General | Maintenance | GHD SiD Register - 63 | Maintenance access | Lack of maintenance access for cycleway and drainage, requiring closure of cycleway to get access or unsafe behaviours in constrained spaces | Accident / injury | Moderate | 2 | Possible | 2 | 2 | Medium | Matt Fairweather | Demonstrate sweeping vehicle passage continuous over entire length. Prove no need to close cycle lanes and hence divert. Consider how to maintain. Minimise with pavement, signage & line markings 04/25 - above incorporated into design where possible. requirements to form part of O&M manuals, transfer to construction | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
33 | Y | Project Wide | General | Operation/ Maintenance | SiD workshop 07/09/23 | Workers in vicinity of live traffic. | Breakdown, damaged assets, incidents. Mowing and general maintenance. | Injury or death | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Travis Medhurst | liaise with asset owners to identify their desired requirements to provide access for maintenance and operations, both during and post construction. Incorporate practical requirements into design e.g. pull off areas, barriers etc. 04/25 - above incorporated into design where possible. requirements to form part of O&M manuals, transfer to construction | Minor | Possible | Medium | Construction | Provide TTM Support for access to maintenance bays/areas i.e. Rolling Blocks , Escorts in/out of areas. If external needing access this needs to be through the comms teams initially |  |  | Unknown |  |  |  | Unknown
34 | Y | Project Wide | General | Operation | TGDD SiD Register - 253 | Debris on road | Natural event causing debris on road | Vehicle accident causing injury or death | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller | 26/03/2025 barriers and available space for minor slips without impacting travel lanes | Minor | Unlikely | Low | Closed |  |  |  | Unknown |  |  |  | Unknown
35 | Y | Project Wide | Geometrics | Maintenance | GHD SiD Register - 25 | Maintenance access | Lack of easy access to ITS masts | Delays in performing maintenance. Lane/road closures required to perform maintenance. | Moderate | 2 | Possible | 2 | 2 | Medium | Daniel Lovisa | Consider hinged poles. Consider cameras that move up/down poles. Cameras not located on highway. Note VMS now removed 04/25 - ongoing 06/08/2025 PC - Access via cycle path and local access. Ongoing development | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
36 | Y | West Bank | Geometrics | Maintenance | TAN-0128 | Service vehicles parked on State highway on / off ramps | Access to traffic signals at interchange | Accident / injury / death from traffic accident | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller | Design to accommodate this. ITS to warn drivers of closures 04/25 - ongoing 06/08/2025 PC - Access provided off the highway. Ongoing development | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
37 | Y | Project Wide | Geometrics | Maintenance | TAN-0063 | Multiple vehicles on maintenance track / shared path along the top of stopbanks with no passing bays. | Interaction between vehicles or vehicles and shared path users | Accident / injury / death from traffic accident | Extreme | 4 | Unlikely | 1 | 3 | High | Mike Pilgrim | Demonstrate sweeping vehicle passage continuous over entire length. Prove no need to close cycle lanes and hence divert. Consider how to maintain. Minimise with pavement, signage & line markings 26/03/25 - to be included in O&M manuals, led by construction team. Possible issue during construction |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
38 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 3 | No separation for any on road cyclists | Tie in to existing SH2 north bound shoulder reduces from 3m to 0.2m | Injury due to cyclist collision with vehicle. | Severe | 3 | Almost Certain | 4 | 4 | Critical | Mike Pilgrim | Remove cyclists. Provision of alternative route HOW ARE CYCLISTS REMOVED, OR WILL THIS JUST TRANSFER ISSUE TO SOMWHERE ELSE????? 26/03/25 - incorporated into design | Severe | Rare | Low | Closed |  |  |  | Unknown |  |  |  | Unknown
39 |  | West Bank | Geometrics | Operation | GHD SiD Register - 14 | Adequate shoulder space on SH2 not provided for breakdowns, maintenance vehicles, emergency services | Road geometry | Lane blocked. Delayed emergency response | Severe | 3 | Likely | 3 | 4 | Critical | Steve Muller | Provide adequate shoulder width. IS THIS A RISK IF ADEQAUTE SHOULDER IS GOING TO BE PROVIED? OR IS IT ACROSS THE WHOLE PROJECT??? 26/03/25 - nominal 1.5m shoulder provided, NZTA accepted 06/08/2025 PC - Nominal 1.5m shoulder width approved by NZTA as per MR's. WTA see ongoing risk to be managed. Ongoing | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
40 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 17 | Tail backs on to highway causing safety issues | Road geometry / unsafe user behaviour | Delays/traffic disruptions. Loss of reputation. | Severe | 3 | Possible | 2 | 3 | High | Steve Muller/ Geoff Prince | Modelling to confirm tail lengths. Provide traffic signal management that eliminates tail backs. 26/03/25 - all ramps exceed MR's, designed out | Minor | Rare | Low | Closed |  |  |  | Unknown |  |  |  | Unknown
41 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 18 | Complex 5-legged signalised intersection | Intersection conflict points. Difficult to phase efficiently and safely | Injury/death from traffic accident. | Extreme | 4 | Unlikely | 1 | 3 | High | Steve Muller | Design changed to PARCLO to minimise conflict points |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
42 | Y | Project Wide | Geometrics | Operation | GHD SiD Register - 42 | Unsafe alignment tie-ins | Tie ins of newly constructed road alignments with existing roads (both during construction and once complete) | Injury / death due to traffic accident | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | Traffic management. Design standards for tie in design. Consider speed reduction / signage Design and construct measures that transition the speed environment so road users react in sufficient timeframe for change. 04/25 - designed out |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
43 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 26 | Excessive side friction demand on high sided vehicles (trucks). | Vertical geometry / crossfall | Potential for overturning vehicle crashes (i.e. Harbour View Road intersection) | Moderate | 2 | Likely | 3 | 3 | High | Steve Muller | Revise design to remove risk 04/25 - designed out |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
44 | Y | Project Wide | Geometrics | Operation | GHD SiD Register - 32 | Conflicts associated with number of turning movements in small area | Priority controlled intersection in close proximity to signals | Injury / death from traffic accident | Moderate | 2 | Likely | 3 | 3 | High | Steve Muller | Current design already incorporated Close Tirohanga. 04/25 - intersection now signalised |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
45 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 34 | Short vertical section leading up to lights at Ewen Bridge | Road geometry | Accident / injury | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller |  |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
46 |  | West Bank | Geometrics | Operation | GHD SiD Register - 35 | Vertical geometry for entry / exit ramps don't meet current design guidance criteria at the proposed Melling bridge | Vertical road geometry | Traffic accident due to limited site distance | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller | Speed management on ramps 04/25 - designed out |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
47 | Y | Project Wide | Geometrics | Operation | GHD SiD Register - 36 | Very low speed horizontal alignment, issues with visibility and ensuring compliance of low speeds at the realigned High St | Road geometry | Traffic accident due to limited site distance | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller | 04/25 - MR design requirements achieved, RSA process part of process 06/25 - Realignment of High Street removed from Alliance scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
48 | Y | Project Wide | Geometrics | Operation | workshop 8/08/23 | Delivery vehicles (and other vehicles) parked over footpaths / shared paths due to lack of parking. | No/ Insufficient parking provision. | Accident / injury to shared path user. | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | Alternative parking areas / loading zones - locations may need to be addressed case by case 04/25 - rail only commercail area in revised scope, loading zones provided |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
49 |  | West Bank | Geometrics | Operation | workshop 8/08/23 | Partial-clover ramp configuration | Unfamiliarity with on / off ramp configuration becomes a hazard to road users | Accident / injury / death from traffic accident | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | Speed management and directional signage This may include additional measures immediately following opening (e.g. VMS) to make road users aware of configuration. 04/25 - TMP to include appropriate requirements, transfer to contractor | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
50 | Y | Project Wide | Geometrics | Operation | workshop 8/08/23 | Infrastructure on the OD route | Oversize vehicles travelling on OD route | Accident/ injury /death due to collision with infrastructure. Damage to asset. Closure of road(s) / SH2 for repairs. | Severe | 3 | Possible | 2 | 3 | High | Steve Muller | Provide clearance for OD requirements. Removable road furniture. ITS structures / signage. Design for impact load. Removal of potential impact areas through longer spans 04/25 - OD envelope provided for in design. TMP to include appropriate requirements, transfer to contractor |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
51 |  | Project Wide | Geometrics | Operation | GHD SiD Register - 33 | Egress from carpark within diverge zone for intersection, number of cross over movements | Road geometry | Accident/injury due to crashes | Moderate | 2 | Possible | 2 | 2 | Medium | Steve Muller | 04/25 - area now out of scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
52 | Y | Project Wide | Geometrics | Operation | TGDD SiD Register - 52 | Public use of maintenance bays | Public stopping or incorrect use of maintenance bays | Accidents | Moderate | 2 | Unlikely | 1 | 2 | Medium | Steve Muller | 04/25 - best practice design applied |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
53 |  | West Bank | Geometrics | Operation | workshop 8/08/23 | Wrong way driver on SH2 | Unsafe user behaviour. Confusion over road layout, signage or line marking. | Vehicle accident causing injury or death | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | Adequate warning signs on ramps Ensure line marking/ approach signage to reduce confusion loop detection of wrong way movement with electronic signs Ensuring adequate space to enable turning around if wrong way - placement of signs to suit this 04/25 - static signs in design, loops being considered 06/08/2025 PC - Appropriate design to deter wrong-way driver | Moderate | Possible | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
54 | Y | West Bank | Geometrics | Operations | SiD workshop 07/09/23 | New intersection layout. | User unfamiliarity leading to crashes. | Injury or death | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | Design to accepted standards and criteria Adopt geometric layout that whilst new to the location, is not a new industry layout 04/25 - above adoted wherever practicable, TMP for opeing | Severe | Unlikely | Medium | Construction | Temporary speed reduction after opening. Warning signage. Signage, line marking. This may include additional measures immediately following opening (e.g. VMS) to make road users aware of configuration. |  |  | Unknown |  |  |  | Unknown
55 | Y | West Bank | Active Modes/Geometrics | Operation | GHD SiD Register - 7 | Poor cyclist / pedestrian provision on Tirohanga Road. | Non-motorised users sharing space with cars on access to S9(2)(a) | Accident / injury | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim | Resolve through redesign Separated provision - designed 04/25 - designed out, 3m path provided |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
56 |  | West Bank | Active Modes/Geometrics | Operation | workshop 8/08/23 | Active modes in the on-ramp corridor | Interaction between active mode user and vehicle. | Accident / injury / death due to collision between active mode user and vehicle. | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Mike Pilgrim | Remove cycles from state highway and/or separate / alternate route. Additional signage for cyclists HOW ARE CONFIDENT CYCLISTS THAT WON&#39;T USE OFF ROAD FACILITES GOING TO BE MANAGED? 04/25 - attractive alternate routes, way finding signage & standard cyclist design parameters incorporated into design |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
57 | Y | Project Wide | Active Modes/Geometrics | Operation | TAN-0063 | Active modes in the maintenance access road | Access road interaction with cycleway. | Accident / injury / death due to collision between active mode user and vehicle. | Extreme | 4 | Possible | 2 | 4 | Critical | Mike Pilgrim | Liaise with construction team to endure design provides opportunity to provide separated cyclist/pedestrian facilities, access points are in safe locations etc. 04/25 - permananet design incoprates best practive where possible. TMP to consider during construction | Moderate | Possible | Medium | Construction | Maintenance access routes to be gated. Suitable alternatives provided. Consider pavement suitability |  |  | Unknown |  |  |  | Unknown
58 | Y | Project Wide | Active Modes/Geometrics | Operation | GHD SiD Register - 6 | Cycleway conflict with driveways and access points - i.e. Riverside carpark access, maintenance access points | Poor cyclist / pedestrian provision | Accident / injury due to collision | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim | Designed out. No driveway/cyclist conflict points. 04/25 - designed out 06/08/2025 PC - No driveway accesses in WTA (Access in HCC area only) |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
59 |  | Project Wide | Active Modes/Geometrics | Operation | workshop 8/08/23 | Pedestrians and cyclists using maintenance access driveways | Steep slopes of maintenance access driveways | Slip / trip / fall when using maintenance access driveways | Minor | 1 | Likely | 3 | 2 | Medium | Mike Pilgrim | Consider gates. Meet vehicle grade requirements to not too steep 04/25 - n/a, area out of scope 06/08/2025 PC - No WTA access. GWRC access only for area R8 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
60 | Y | Project Wide | Active Modes/Geometrics | Operation | SiD workshop 07/09/23 | Cyclists travelling north not accommodated | Conflict with vehicles | Injury/death | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Mike Pilgrim | DOES THE DEIGN NEED TO BE AMENDED TO INCLUDE ALLOWANCE??? IS IT A &#39;PROJECT WIDE&#39; ISSUE? 04/25 - duplicate of 038 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
61 | Y | West Bank | Geometrics | Operation | GHD SiD Register - 38 | Need for F-Type TL5 barriers, which have less energy dissipating ability and increase the severity of any crashes compared with other barrier forms (noting reduced maintenance from TL5 barriers) | Road geometry space constraints | Injury / death from collision with barrier | Moderate | 2 | Likely | 3 | 3 | High | Mike Pilgrim | Concrete barrier requires less maintenance during life cycle. Revise design to remove risk 04/25 - design minimises non concrete barrier, mTL5 only on bridge or where necessary | Moderate | Unlikely | Medium | Closed |  |  |  | Unknown |  |  |  | Unknown
62 | Y | Project Wide | Traffic & Transport | Construction | SiD workshop 07/09/23 | Unsuitable diversion routes. | Traffic diverted onto unsuitable routes. Unfamiliar routes. | Injury, accident. Traffic delays, further disruption to traffic. | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | Liaise with construction team to identify preferred routes, model to evaluate appropriateness and localised improvement requirements. This to include route capacity, route alignment and length, land use etc 04/25 construction TMP to take this onto consideration | Extreme | Possible | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
63 | Y | Project Wide | Active Modes | Operation | workshop 8/08/23 | Different user types and abilities on shared path | Interaction between shared path users (e.g. cyclists, pedestrians, commuters, recreational users, disabled users, e-motorised vehicles etc). | Accident / injury / death due to collision between shared path users | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim | Separate walking and cycling lanes and/or provide best practice shared use path widths to allow all mode of transport using SUP to do so as safely and as efficiently as possible 04/25 design incorporates above where possible 06/08/2025 PC - Segregate cyclepath in WTA. Maintenance methodology i.e. sweeping / lighting / cabinet openings / vegetation to be assessed to minimise impact | Minor | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
64 | Y | Project Wide | Active Modes | Operation | workshop 8/08/23 | Shared use electric scooters left in pathways | Shared use electric scooters left in pathways become a hazard to blind/vision impaired, mobility impaired and disabled people. | Accident / injury due to collision with electric scooters left in pathway | Moderate | 2 | Possible | 2 | 2 | Medium | Mike Pilgrim | 04/25 - design incorporates best practice 06/25 - HCC, no e-scooter companies in lower hutt at present | Moderate | Possible | Medium | Closed |  |  |  | Unknown |  |  |  | Unknown
65 | Y | Project Wide | Active Modes | Operation | workshop 8/08/23 | Active mode users crossing road at unsafe locations | Minimised road crossings | Accident / injury / death due to collision between pedestrian / active mode user and vehicle. | Extreme | 4 | Possible | 2 | 4 | Critical | Mike Pilgrim | Optimise design with relation to desire lines - actioned. Provide barriers etc in areas where cross points do not align with desire lines 04/25 - design incorporates best practice 06/08/2025 PC - Ongoing | Minor | Unlikely | Low | Open |  |  |  | Unknown |  |  |  | Unknown
66 | Y | Project Wide | Active Modes | Operation | GHD SiD Register - 22 | Safety and comfort of pedestrians, cyclists and road users compromised | Poor cyclist / pedestrian provision | Accident / injury due to collision | Moderate | 2 | Possible | 2 | 2 | Medium | Mike Pilgrim | 04/25 - design incorporates best practice, ongoing liaison with relevant asset owners 06/08/2025 PC - Accessibility incorporated in design. Disability action group (Vision & mobility impaired organisations) have been engaged to inform design. Ongoing | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
67 | Y | Project Wide | Active modes | Operation | SiD workshop 07/09/23 | Cyclist conflict with vehicles. | Commuter and road cyclists not using cycleways if not efficient. | Injury/death. | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Mike Pilgrim | Separate cyclists from traffic but not compromise their speed/trip duration to work. Make cycleway desirable - allow fast riding leading to Melling to Petone Cycleway. Make facility wide enough to use mechanical sweeper. Provide good connection to the Melling cycleway. 04/25 - design incorporates above wherever practicable 06/08/2025 PC - Off-road facility to be desirable without making road less safe. To consider operation through interchange. Ongoing | Extreme | Unlikely | High | Open - Managed | Ensure cyclists have a valid route during construction. |  |  | Unknown |  |  |  | Unknown
68 | Y | Project Wide | Active Modes/Geometrics | Operation | GHD SiD Register - 24 SiD workshop 07/09/23 | Poor cycle connectivity between off-road paths and local roads. Including access paths not fit for dual purpose. | Poor cyclist / pedestrian provision. Conflict/unsafe movements of different user groups (e.g. walkers, cyclists, commuters) | Accident / injury due to collision | Moderate | 2 | Possible | 2 | 2 | Medium | Mike Pilgrim | Split use accessways. 04/25 - ongoing 06/08/2025 PC - Not captured under WTA asset. Ongoing work with temporary active modes. | Moderate | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
69 | Y | Project Wide | Urban Design & Landscape | Operation | GHD SiD Register - 30 | Unsafe user behaviour | People loitering in the Riverside carpark after hours | Safety issues | Moderate | 2 | Possible | 2 | 2 | Medium | Nicole Thompson | 06/25 - Hcc, removed from alliance scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
70 | Y | Project Wide | Urban Design & Landscape | Operation | TAN-0013 | Streetscape - introduction of new shared space | Unfamiliarity with new shared space presents challenges for vision impaired, mobility impaired, disabled or neurodiverse people. | Accident / injury due to unfamiliarity navigating new shared space. | Moderate | 2 | Possible | 2 | 2 | Medium | Nicole Thompson | Vision & mobility impaired organisations will be consulted, potentially including post construction 04/25 - ongoing 06/08/2025 PC - Vision & mobility impaired organisations engaged through the design process using best practice for local road. Ongoing | Minor | Unlikely | Low | Open |  |  |  | Unknown |  |  |  | Unknown
071a | Y | Project Wide | Urban Design & Landscape | Operation | workshop 8/08/23 | CPTED measures do not deter criminals Movement restrictions in locations where crime is increased due to low level of lighting and CCTV e.g. narrow spaces under bridges. | Unsafe user behaviour. People loitering in carpark if carpark is visually recessive space. Movement restrictions in locations where crime is increased due to low level of lighting and CCTV e.g. narrow spaces under bridges. Safety risk for homeless/criminal activity under the bridge or either side of the stopbank. | Harm to person or damage / vandalism to assets. Injury or death | Extreme | 4 | Possible | 2 | 4 | Critical | Nicole Thompson | Bridge form selection to deter access. Provision of alternative desirable areas. CCTV presence. Lighting design extent and specifications. Removal of high walls, dead ends. Low planting. 10/04/25 Independent CPTED review, ongoing 06/08/2025 PC - Review suggests higher lighting levels does not deter criminal activity. Lighting levels to be determined to provide appropriate level. CCTV deterrent to be considered where it can be monitored appropriately. Ongoing | Extreme | Unlikely | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
72 | Y | Project Wide | Urban Design & Landscape | Operation | SiD workshop 07/09/23 | Movement restrictions in locations where crime is increased due to low level of lighting and CCTV e.g. narrow spaces under bridges. | Safety risk for homeless/criminal activity under the bridge or either side of the stopbank. | Injury or death | Extreme | 4 | Likely | 3 | 4 | Critical | Nicole Thompson | 06/25 - HCC, duplicate of 71a and 71b |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
73 | Y | Project Wide | Urban Design & Landscape | Maintenance | workshop 8/08/23 | Landscape Maintenance/ maintenance of urban design elements. | Landscape maintenance on steep slopes, around retaining walls and in road shoulders - increased risk around activities involving lane closure, working at heights. Lighting maintenance. Bridge design. | Accident / injury due to fall from height, traffic impact. | Severe | 3 | Possible | 2 | 3 | High | Nicole Thompson | Low maintenance planting and retaining wall finishes. Reduce number of steep slopes. Provide more space between retaining wall and live carriageway. Alternative accessways 06/08/2025 PC - Remove planting at top of abutment to remove risk to maintenance operators. Ongoing | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
74 | Y | River Works | Urban Design & Landscape | Maintenance | GHD SiD Register - 44 | Maintenance of urban design elements in the river corridor | Urban design elements that need continual cleaning from the river | Accident / injury / death due to drowning | Extreme | 4 | Rare | 0 | 3 | High | Nicole Thompson | cancelled, now out of scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
75 | Y | River Works | Environmental/Planning | Construction | workshop 8/08/23 | Harm to species in river corridor | Contamination to river due to construction activities | Harm to species in river corridor | Moderate | 2 | Almost Certain | 4 | 3 | High | Kim Hardy | ESCP. Adopt good construction practices. Anti-leak valves. EWP Using precasting material reduce works in river. Try to work in the dry e.g. cofferdam. Material selection for low toxicity. Minimise excavations. Stabilise as soon as possible. SSESCP. Monitoring rainfall and reviewing measures to ensure risk is minimised. |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
76 | Y | River Works | Environmental/Planning | Construction | GHD SiD Register -2 | Contamination of water | Construction works (i.e. bridge piling, ground improvements, refuelling activities close to the river) | Water quality within aquifer is decreased. | Extreme | 4 | Possible | 2 | 4 | Critical | Kim Hardy | Adopt good practice and design to minimise risk. Main risk to be addressed with construction controls. Installing proprietary devices early. Staging to consider timing of stormwater systems. ESCP. Adopt good construction practices. Anti-leak valves. EWP Using precasting material reduce works in river. Try to work in the dry e.g. cofferdam. Material selection for low toxicity. Minimise excavations. Stabilise as soon as possible. SSESCP. Monitoring rainfall and reviewing measures to ensure risk is minimised. | Moderate | Possible | Medium | Construction | Expect risk to increase for construction with appropriate protocols implemented to minimise risk |  |  | Unknown |  |  |  | Unknown
77 | Y | River Works | Environmental/Planning | Construction | GHD SiD Register - 9 | Contamination of water | Construction works (i.e. stormwater outlets discharge contaminants from the works, poor refuelling practices close to the river, increased sedimentation through in-river works) | Water quality within the river / streams is decreased. | Severe | 3 | Possible | 2 | 3 | High | Kim Hardy | Adopt good practice and design to minimise risk. Main risk to be addressed with construction controls. Anti-leak valves. EWP Using precasting material reduce works in river. Try to work in the dry e.g. cofferdam. Material selection for low toxicity. Minimise excavations. Stabilise as soon as possible. SSESCP. Monitoring rainfall and reviewing measures to ensure risk is minimised. |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
78 | Y | River Works | Environmental/Planning | Natural Disaster | workshop 8/08/23 | Harm to species in river corridor | Contamination to river during a flood event | Harm to species in river corridor | Severe | 3 | Unlikely | 1 | 2 | Medium | Kim Hardy | Stick to minimum requirements. Design to reduce risk of contamination. ESCP. Adopt good construction practices. Anti-leak valves. EWP Using precasting material reduce works in river. Try to work in the dry e.g. cofferdam. Material selection for low toxicity. Minimise excavations. Stabilise as soon as possible. SSESCP. Monitoring rainfall and reviewing measures to ensure risk is minimised. |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
79 |  | Bridges | Geotechnical | Construction | SiD workshop 07/09/23 | Piling methodology | Consented piling methodology requires divers to enter casing to confirm seal. | Death | Extreme | 4 | Possible | 2 | 4 | Critical | Russell Allison | Remove piles. Consent alternate piling method. DOES THIS MEAN THAT A PLAN B METHODOLOGY IS GOING TO BE CONSNETNED AHEAD OF CONSTRCUTION? 09/04/2025 Alternate pile methodology approved which removes the need for divers. |  |  | Unknown | Closed | Remote control operations. |  |  | Unknown |  |  |  | Unknown
80 |  | Project Wide | Geotechnical | Construction | TG SiD Register - 1 | Slope instability. Landslides/rockfall during construction. | Adverse ground conditions, rainfall or seismic event. | Failure debris impacts person or plant. | Extreme | 4 | Likely | 3 | 4 | Critical | Russell Allison | Rockfall protection measures for SH2 Ensure design provides provision/space to allow safe construction practices to be implemented e.g. access tracks, rope access, temporary works to contain fallen material without impacting on traffic etc. 09/04/25 Design reduces risk where possible, residual risk is a construction risk | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
81 |  | Project Wide | Geotechnical | Construction | SiD workshop 07/09/23 | Construction of shallow foundation for bridge in the river corridor. | Flooding of excavation during construction. | Injury or death from flood debris. | Extreme | 4 | Likely | 3 | 4 | Critical | Russell Allison/ Kelsy Seyb | Design of cofferdam to prevent flood water and resist flood debris. 14/04/25 Transfer to construction team |  |  | Unknown | Cancelled | Flood management plan and awareness of personnel. Inspections of cofferdam. Procedures for personnel entering excavation. |  |  | Unknown |  |  |  | Unknown
82 |  | Project Wide | Utilities | Operation | TGDD SiD Register - 123 | Working with live services. Utilities damage including gas main rupture or overhead power poles damaged | Moderate earthquake generates liquefaction causing differential settlement of buried services or affecting foundations. May include buoyancy effects on dried utilities (e.g. gas main) | Impact injury. Electrocution. Loss of containment (gas) | Extreme | 4 | Possible | 2 | 4 | Critical | Graeme Doherty | Comprehensive service model. Potholing and design contingency. Ground improvement to consider utilities. 08/25 design includes measures to reduce possibility wherever practicable, e.g. standard clearances, tracer wire for gas main etc. construction risk | Severe | Unlikely | Medium | Construction | Temporary diversions to remove risk. Loss of containment does sometimes occur after an earthquake. Use HDPE - Isolation valves at critical locations - out of traffic. |  |  | Unknown |  |  |  | Unknown
83 |  | Project Wide | Geotechnical | Maintenance | TAN-0063 | Slope maintenance | Maintenance of steep / landward slopes areas with retaining | Accident / injury to workers completing maintenance / remedial works on slopes | Moderate | 2 | Likely | 3 | 3 | High | Russell Allison | Low maintenance planting. Fixing points for maintenance workers. Reduce number of steep slopes 04/25 Design includes appropriate measures where required. transfer to construction for O&M | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
84 |  | Project Wide | Geotechnical | Construction | TGDD SiD Register - 183 | Adverse groundwater conditions | Adverse groundwater conditions lower factor of safety 09/04/25 deep excavation minimised in design, work with construction team as necessary | Impact injury. | Extreme | 4 | Unlikely | 1 | 3 | High | Russell Allison | Work with the contractor for ground water control measures. Ensure trench stability. 04/25 design includes measures where possible, transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
85 |  | Project Wide | Geotechnical | Construction | TGDD SiD Register - 184 | High and steep slopes formed in adverse ground. | Adverse/unforeseen ground conditions | Impact injury | Extreme | 4 | Possible | 2 | 4 | Critical | Russell Allison | Staged assessment of slope during excavation. 04/25 site investigations reduce likelihood, high steep slopes reduced in quantity (1 at 9m high). constrcution risk | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
86 |  | Project Wide | Geotechnical | Operation | TAN-0031 | Foundation performance | Geotechnical elements supporting design assets | Accident / injury / death from failure of asset | Extreme | 4 | Unlikely | 1 | 3 | High | Russell Allison | Design to codes & standards, verification and construction monitoring. Appropriate GI before design 04/25 Design has applied good practices and design codes and standards, risk reduced as far as practicable 06/08/2025 PC - Design of slopes being worked through for slope stability, etc. Ongoing | Severe | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
87 |  | Project Wide | Geotechnical | Operation | TAN-0032 | Contamination / depressurisation of Waiwhetu aquifer | Ground improvements found to be required on top of Waiwhetu aquifer | Waiwhetu aquifer supplies a significant portion of public freshwater supply, so contamination / depressurisation could have significant health impacts | Severe | 3 | Possible | 2 | 3 | High | Russell Allison | Sufficient ground investigations / proof bore. Groundwater monitoring. Grouting to fix issue. Design to minimise interaction (AAIMP to resolve issues) 04/25 no GI into aquifer |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
88 |  | Project Wide | Geotechnical | Operation | TGDD SiD Register - 2 | Slope instability. Landslides/rockfall during operation of the State Highway. | Adverse ground conditions, rainfall or seismic event. | Failed materials impacts road user. | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Russell Allison | SH2 rockfall protection. 04/25 Design has applied good practices and design codes and standards, risk reduced as far as practicable 06/08/2025 PC - Catch fence included on SH2, hillside. Maintenance to clear any rocks caught/U-drain will require lane closures - frequency to be minimised. Ongoing maintenance requirement | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
089a |  | Project Wide | Geotechnical | Operation | TGDD SiD Register - 3 | Slope instability. Landslides/rockfall during performance of maintenance. | Adverse ground conditions, rainfall, seismic event or tree jacking. | Failure material impacts person or plant. | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Russell Allison | Rockfall protection, provide egress routes, 04/25 - Design has applied good practices and design codes and standards, risk reduced as far as practicable | Moderate | Rare | Low | Open - Managed | Include risks and operational requirements in O&M manuals including measure such as geotechnical evaluation of risk prior to commencing any work |  |  | Unknown |  |  |  | Unknown
90 |  | Project Wide | Geotechnical | Natural Disaster | TAN-0031 | New fill slopes performance in extreme seismic events | Earthquake or seismic event causing instability. | Injury or death. Damage to assets. Road closures. | Extreme | 4 | Rare | 0 | 3 | High | Russell Allison | Design to codes & standards. Minimise high risk slopes, establish and follow project seismic design philosophy 04/25 - Design has applied good practices and design codes and standards, risk reduced as far as practicable 06/08/2025 PC - Incorporate best practice and PR's. Ongoing | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
91 |  | Project Wide | Geotechnical | Natural Disaster | TAN-0031 | New cut slopes performance in extreme seismic events | Earthquake or seismic event causing instability. | Injury or death. Damage to assets. Road closures. | Extreme | 4 | Rare | 0 | 3 | High | Russell Allison | Design to codes & standards. Minimise high risk slopes, establish and follow project seismic design philosophy 04/25 - Design has applied good practices and design codes and standards, risk reduced as far as practicable | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
92 |  | Project Wide | Geotechnical | Natural Disaster | workshop 8/08/23 | Existing slopes (particularly in Western Hills) and performance in extreme seismic event. | Earthquake or seismic event causing instability. | Injury or death. Damage to assets. Road closures. | Extreme | 4 | Rare | 0 | 3 | High | Russell Allison | Access existing slopes, keep away from slopes. Barriers to prevent debris flow or other mitigation. Design of pathways below 04/25 - Design has applied good practices and design codes and standards, risk reduced as far as practicable | Severe | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
93 |  | Project Wide | Geotechnical | Natural Disaster | workshop 8/08/23 | Batter slope angle and height of stopbank. | Alignment / geometry of stopbank. Alignment / geometry of shared path. Adverse weather (strong winds, rainfall). | Shared path users fall from path and are unable to self-arrest leading to injury. | Moderate | 2 | Likely | 3 | 3 | High | Russell Allison | Slopes generally 1:3 to avoid injury. Handrails where steeper (i.e. 1:1.5). Path widths and shoulders 04/25 closed from geotech perspective |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
94 |  | Project Wide | Geotechnical | Natural Disaster | TAN-0032 | Failure of structures or road | Insufficient ground improvement as a result of limited investigations and assessment / changes to liquefaction assessment | Accident / injury / death from failure of asset in an earthquake or seismic event | Extreme | 4 | Unlikely | 1 | 3 | High | Russell Allison | Significant investigation / proof bores. Construction monitoring. Verification. Consider bridge form used. 04/2025 closed | Extreme | Rare | High | Closed |  |  |  | Unknown |  |  |  | Unknown
95 |  | Project Wide | Geotechnical | Natural Disaster | TAN-0032 | Failure of stopbanks | No ground improvements proposed beneath the stopbank | Accident / injury / death from increased flood extents due to failure of stopbank | Extreme | 4 | Rare | 0 | 3 | High | Russell Allison | Repair strategy to access and repair stopbanks within short period. 04/25 out of scope | Extreme | Rare | High | Cancelled |  |  |  | Unknown |  |  |  | Unknown
96 |  | Project Wide | Geotechnical | Natural Disaster | TAN-0033 | Differential settlement of existing and proposed stopbanks | Previous consolidation effects where proposed stopbank adjacent to existing stopbank | Accident / injury due to uneven ground levels Reduced effectiveness of stopbanks in containing flood water | Minor | 1 | Likely | 3 | 2 | Medium | Russell Allison | Maintenance to top up footpath. Appropriate design of surfacing materials for paths 04/2025 overbuild to allow for post construction settlement. O&M manual to monitor and top up as/if required | Minor | Unlikely | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
97 | Y | West Bank | ITS/Lighting/CCTV | Maintenance | SiD workshop 07/09/23 | Maintenance to CCTV on SH2 | No provision for maintenance access e.g. MABs | Injury or death | Extreme | 4 | Likely | 3 | 4 | Critical | Daniel Lovisa | Move CCTV to cycle track, off of the SH2 network. 04/25 - design incorporates best practice, ongoing liaison with relevant asset owners 06/08/2025 PC - CCTV moved to cycletrack. To confirm works are to MRs. (ITS design to include WTA review at 50% to determine maintenance requirements). Ongoing | Minor | Unlikely | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
098a | Y | Project Wide | ITS/Lighting/CCTV | Operation | TGDD SiD Register - 282 | Underground services | Lighting column foundations clashing with existing services/utilities | Injury or possible death | Severe | 3 | Possible | 2 | 3 | High | Lindsay Young | Clash detection - in 3D model minimising size of foundations to reduce likelihood of clashing Relocate lighting column/ services to avoid clash Utilities potholing/ surveying 04/25 - design includes above where practicable. construction risk also 06/08/2025 PC - 3D modelling incorporated to improve clash detection and provide clear access points. Ongoing | Severe | Possible | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
99 | Y | Project Wide | ITS/Lighting/CCTV | Operation | TGDD SiD Register - 283 | Lighting columns | Vehicle impact on lighting columns positioned adjacent to traffic lanes and/or within trafficable area | Injury or possible death | Extreme | 4 | Possible | 2 | 4 | Critical | Lindsay Young | Locate poles outside of trafficable carriageway Position lighting column behind barrier Frangible poles Reduce speed limit to reduce likelihood/ severity of impact (unlikely) 04/25 - design incorporates best practice, ongoing liaison with relevant asset owners 06/08/2025 PC - Design to best practice. Potential departure(s) i.e. column in break in rigid barrier. Early consultation with WTA to be instigated. Ongoing | Minor | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
100 |  | Project Wide | ITS/Lighting/CCTV | Operation | TGDD SiD Register - 284 | Lighting columns | Vehicle impact to barrier end-terminal, subsequently impact to lighting columns | Injury or possible death | Severe | 3 | Possible | 2 | 3 | High | Lindsay Young | 04/25 - double up with 099 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
101 |  | Bridges | ITS/Lighting/CCTV | Operation | workshop 8/08/23 | Limited lighting on Te Awa Kairangi Pedestrian Bridge | Limited lighting on Te Awa Kairangi Pedestrian Bridge | Active mode users crossing the bridge at night feel or are unsafe. Accident / injury due to low visibility | Moderate | 2 | Possible | 2 | 2 | Medium | Lindsay Young | 04/2025 - removed from scope of work |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
102 |  | Project Wide | ITS/Lighting/CCTV | Operation | TAN-0063 | Limited lighting within stopbank | Limited lighting within stopbank | Active mode users near stopbank at night feel or are unsafe. Accident / injury due to low visibility | Moderate | 2 | Almost Certain | 4 | 3 | High | Lindsay Young | Solar rocks / lighting. Provide CCTV. 04/25 - out of scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
103 |  | River Works | ITS/Lighting/CCTV | Operation | workshop 8/08/23 | Alternative light options in river corridor | Lighting requirements do not allow for poles in the river corridor. | Active mode users near river corridor at night feel or are unsafe. Accident / injury due to low visibility | Minor | 1 | Likely | 3 | 2 | Medium | Lindsay Young | 04/25 - out of scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
104 |  | West Bank | Rail | Design | KiwiRail SiD Register - 21 | Minimum KiwiRail track clearances | Insufficient clearance | Infrastructure damage / injury / death | Extreme | 4 | Likely | 3 | 4 | Critical | Blair Rogers | Clearances to be maximised where possible but all design clearances will meet KiwiRail standards, including approved departure. Install security fences where required 06/25 KiwiRail requirements plus construction tolerances etc. applied to design, clearance risk minimal. Departure from standard for pinch point. | Severe | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
105 |  | West Bank | Rail | Design | KiwiRail SiD Register - 20 | Interface between the designer (Alliance) and KiwiRail's signalling team. | Resourcing signal design, insufficient signal sighting checks against modified structures | Design delays. Safety concerns / injury | Severe | 3 | Likely | 3 | 4 | Critical | Blair Rogers | Coordination with KiwiRail Signalling Team during design for any external information. Signalling requires relocation of one signal and ground equipment. 06/25 KiwiRail requirements plus construction tolerances etc. applied to design, clearance risk minimal | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
106 |  | West Bank | Rail | Design | KiwiRail SiD Register - 24 | Delays in testing / commissioning | Provision of LV power feed for the signal cubicle (service limit board) to be included | Service disruptions | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | Melling Line will be closed. 06/25 - no longer applicable, adequate time to commission. Exception being LV design across network which is to be confirmed. |  |  | Unknown | Open - Managed | Melling Line will be closed for the duration of construction and commissioning. To remain on register to be reviewed if any live line work is required. |  |  | Unknown |  |  |  | Unknown
107 |  | West Bank | Rail | Design | KiwiRail SiD Register - 25 | Positive feeder fall | Risk of positive feeder fall zone not considered in design | Significant service disruptions and or serious / fatal injuries | Extreme | 4 | Unlikely | 1 | 3 | High | Blair Rogers | Design to follow KiwiRail standards, if any infrastructure is within the fall zone it will be bonded appropriately. 06/25 KiwiRail requirements plus construction tolerances etc. applied to design, clearance risk minimal | Extreme | Rare | High | Open - Specified |  |  |  | Unknown |  |  |  | Unknown
108 |  | West Bank | Rail | Construction | TAN-0150 KiwiRail SiD Register -1 | Working around live rail | Work required adjacent to live rail corridor. Numerous stages, changes to tracks, logistics for trains including the interface with pedestrians at an operating station. This may lead to an unsafe environment for construction workers and the public | Injury / death due to train derailment, collision with train, construction vehicles colliding with public. | Extreme | 4 | Possible | 2 | 4 | Critical | Blair Rogers | Design to minimise construction work required in rail corridor and future maintenance. Assessment during design for risk of de-railment and any controls required. KiwiRail review and approvals for all siting and operation of infrastructure in the rail corridor. Primarily a construction risk, expected to be higher than design 06/25 Transfer to construction team, site will be construction zone, many kiwirail assets removed prior to construction starting. early works, if required, may require block of line prior to programmed line closure |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
109 |  | West Bank | Rail | Construction | workshop 8/08/23 | Rail corridor construction works | Rail corridor construction works required that is not block of lines | Injury / death due to collision with train | Extreme | 4 | Possible | 2 | 4 | Critical | Blair Rogers | Design to minimise construction work required in rail corridor and future maintenance. Assessment during design for risk of de-railment and any controls required. KiwiRail review and approvals for all siting and operation of infrastructure in the rail corridor. Primarily a construction risk, expected to be higher than design 06/25 Transfer to construction team, site will be construction zone, many kiwirail assets removed prior to construction starting. early works, if required, may require block of line prior to programmed line closure |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. All works within shut down. If minor work outside the shut down then it will be undertaken to all KiwiRail permit to Enter conditions for safe operation |  |  | Unknown |  |  |  | Unknown
110 |  | West Bank | Rail | Construction | GHD SiD Register -11 | Excavator strike of OLE / installation of steel barriers, signs and lighting columns | SH2 construction close to live rail | Injury / death due to collision with drain, contact with OLE | Severe | 3 | Possible | 2 | 3 | High | Blair Rogers | Melling Line will be closed. From online team: Melling line will be Partially closed. - Requirement for delapidation assessments pre and post works on infrastructure to be re-used - seek contractors with capabilities such as digital shielding to protect personnel and assets 6/25 construction risk. need to check programme for SH2 v's rail, primarily for road construction risk |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
111 |  | West Bank | Rail | Construction | KiwiRail SiD Register - 3 | Working at heights | During construction of canopies, workers will be at height. | Fall causing injury/fatality. | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | Reduce at height work where possible in the design. More in Construction controls for on-site activities. 06/25 design incorporates above, risk transfer to construction | Moderate | Unlikely | Medium | Construction | Safe working methodology for construction of all at height areas. |  |  | Unknown |  |  |  | Unknown
112 |  | West Bank | Rail | Construction | KiwiRail SiD Register - 22 | Realignment / diversion of fibre connections to new signalling cabinet location | Existing KiwiRail fibre connections are located on poles along the existing alignment. | Service disruptions - stops trains. | Severe | 3 | Unlikely | 1 | 2 | Medium | Blair Rogers/ Graeme Doherty | Melling Line will be closed. Temporary diversions to remove risk. From online team: Melling line will be Partially closed. 06/25 construction risk. note potential for underground cable to remain, treat as live unless verified otherwise |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
113 |  | West Bank | Rail | Construction | KiwiRail SiD Register - 23 | Interruption of live services | Potential conflict with KiwiRail ducting under the Normandale bridge to be verified by the designer (Alliance). Ducting carries vital KiwiRail fibre assets. | Failure may lead to significant service disruptions / damage | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | Melling Line will be closed. From online team: Melling line will be Partially closed. 06/25 construction risk |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
114 |  | West Bank | Rail | Construction/ Maintenance | GHD SiD Register - 16 | Working around live rail and live OLE masts and services | Space available for any rail corridor drainage or ballast changes associated with the rail realignment works | Injury / death due to electrocution or collision with train | Extreme | 4 | Likely | 3 | 4 | Critical | Blair Rogers | Melling Line will be closed. From online team: Melling line will be Partially closed. 06/25 construction risk |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
115 |  | West Bank | Rail | Construction/ Maintenance | GHD SiD Register - 57 | Undue pressure on site to meet block of line requirements | Timing of line closures for key works - inadequate planning and timeframes | Accident / injury resulting from rushed work | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | Melling Line will be closed. From online team: Melling line will be Partially closed. 06/25 construction risk, regular planning meetings underway for closure |  |  | Unknown | Construction | Melling Line will be closed for the duration of construction and commissioning. |  |  | Unknown |  |  |  | Unknown
116 |  | West Bank | Rail | Maintenance | SiD workshop 07/09/23 | Harm to cyclists and maintenance workers. | Restricted access to rail corridor/cycleway at pinch point. | Accident. | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | Access gates will be installed either side of the pinch points. All operational maintenance will be covered under agreement between all parties. Potentially under full block of line for rail works - to meet KiwiRail requirements. 06/25 design incorporates above, transfer to construction & for O&M's | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
117 |  | West Bank | Rail | Maintenance | KiwiRail SiD Register - 9 / KiwiRail PSHL Rev B | Slips / trips and falls during maintenance of infrastructure (in particular the OLE masts) | Ballast walking surface in rail corridor. Maintenance staff have to traverse over rail line or have narrow maintenance tracks | Injury caused by slip/trip/fall | Minor | 1 | Likely | 3 | 2 | Medium | Blair Rogers | 1. Maintenance person to use cycle way instead of rail corridor for access. 2. Design to include maintenance access gates at points of routine obvious maintenance e.g. signals, grease pots. 06/25 design incorporates above, transfer to construction to include in O&M's | Minor | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
118 |  | West Bank | Rail | Maintenance | KiwiRail SiD Register - 17 / KiwiRail PSHL Departure Rev B | During maintenance of the rail infrastructure KiwiRail staff may be struck by rail vehicle (3m-5m instead of 5m clearance - Km1.640 to 2.350) and or road vehicles (in particular the area below the Normandale bridge) | Insufficient clearance in rail corridor for maintenance person (between rail vehicle and fence). Maintenance worker does not comply with safe working procedures for the rail corridor. Maintenance worker strays onto track and/or unaware of approaching rail vehicle when accessing the rail corridor through the maintenance access gates. | Injury/Fatality | Extreme | 4 | Possible | 2 | 4 | Critical | Blair Rogers | 1.. Design to include signage to warn maintenance personnel of reduced clearance. 2. Design to include access gates from cycle way into rail corridor 3. Access gate width to allow sufficient clearance to DKE. 4. Recommend maintenance activities in rail corridor follow current procedures and are restricted to (BOL) or non operational hours where practical. Access for maintenance for light vehicles may be permitted along the cycle path, limitations and control measures to be agreed with Waka Kotahi. 06/25 Design incorporates above, transfer to construction team to include in O&M's | Extreme | Rare | High | Construction | Include risks and operational requirements in O&M manuals. |  |  | Unknown |  |  |  | Unknown
119 |  | West Bank | Rail | Maintenance | KiwiRail PSHL Rev B | Measures for maintaining the new fence cause interference /encroachment into the rail corridor, i.e. <3.0m width) | 1. Insufficient clearance in rail corridor for maintenance person (between rail vehicle and fence). 2. Maintenance worker does not comply with safe working procedures for the rail corridor. 3. Maintenance worker strays onto track and/or unaware of approaching rail vehicle when accessing the rail corridor through the maintenance access gates. 4. Cycle path users gain access to the rail corridor | Maintenance worker struck by train. Member of public encroaches into rail corridor and is struck by a train. Encroachment within the Minimum Approach Distance (MAD) 2m for people and equipment. 4m for plant to OHW | Extreme | 4 | Unlikely | 1 | 3 | High | Blair Rogers | 1. This activity would be scheduled to suit non-operating times . 2. The fence is reinstated at the end of each working period (temp or permanent) 3. KR Maintenance Access gates to be installed at suitable locations to allow safe access and exit 4. Access gates to have KiwiRail TA padlocks 06/25 Design incorporates above, transfer to construction team to include in O&M's | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
120 |  | West Bank | Rail | Operation / Maintenance | KiwiRail SiD Register - 18 | Risk of accidental touch potential to both cyclists and maintenance staff. | Insufficient touch protection | Injury | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | Design to follow KiwiRail standards, if any infrastructure is within the fall zone it will be bonded appropriately. 06/25 design meets KiwRail standards | Extreme | Rare | High | Open - Specified |  |  |  | Unknown |  |  |  | Unknown
121 |  | West Bank | Rail | Operation | GHD SiD Register - 12 | Earthing and bonding of rail services | Earthing and bonding design not considered re. OLE alongside rail - i.e. cyclist fences, cyclist contact directly, cycle lighting columns, road lighting columns and steel barriers | Injury / death due to electrocution | Extreme | 4 | Possible | 2 | 4 | Critical | Blair Rogers | Design will meet all KiwiRail OLE related standards to ensure safer operation. 04/25 design meets KiwRail standards, air gaps will be provided for any fence less than 2m 06/25 Signage added for air gaps "isolating panel do not connect to adjacent posts". air gaps provided for any fence less than 2.5m | Extreme | Rare | High | Open - Specified |  |  |  | Unknown |  |  |  | Unknown
122 |  | West Bank | Rail | Operation | GHD SiD Register - 29 | Train not stopped at end of the line | Relocation of friction buffer stop not suitably accommodated during design | Accident / Injury. Damage to train carriage, rails or surrounding infrastructure | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | Buffer stop has been upgraded and will be installed to meet design requirements. 06/25 existing buffer will be upgraded in design, and will be relocated | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
123 |  | West Bank | Rail | Operation | TAN-0150 | Fall from retaining walls adjacent to railway | Height of retaining walls adjacent to railway | Accident / injury due to fall from top of retaining wall | Extreme | 4 | Possible | 2 | 4 | Critical | Blair Rogers | Cycleway walls will be fully fenced, therefore no hazard. SH2 side walls to be assessed to meet current Waka Kotahi standards for the motorway Current SH2 edge treatment is barrier only no fence (full length from Melling Station to Normandale Bridge. KiwiRail/NZTA fencing standard to be consistent 06/25 need to check against geometric design (s 9(2)(a)) from a cycleway perspective | Extreme | Unlikely | High | Open |  |  |  | Unknown |  |  |  | Unknown
124 |  | West Bank | Rail | Operation | workshop 8/08/23 / KiwiRail SiD Register - 10 / KiwiRail PSHL Rev B | People trespassing on the rail corridor or throwing things on to it | Unsafe user behaviour, climbing existing fencing or accessing the corridor where there is no fence. | Accident / injury / death due to collision with train or electrocution from lines. | Extreme | 4 | Likely | 3 | 4 | Critical | Blair Rogers | 1. Provision of a 1.8m high chain-link fence between the cycle path and the rail corridor is being provided. 2. Access gates for maintenance to be locked using KiwiRail TA Lock. 3.CCTV and Lighting will be provided 4. Passive surveillance from SH2 06/25 need to check against geometric design (s 9(2)(a)) from a cycleway perspective | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
125 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 6 | Clearance between track centreline and infrastructure | Insufficient clearance | Train colliding with infrastructure causing damage / injury | Moderate | 2 | Almost Certain | 4 | 3 | High | Blair Rogers | Compliance with KiwiRail clearances. KiwiRail review and acceptance. 3D modelling (federated) with clash detection. 04/25 - duplicate of 104 |  |  | Unknown | Cancelled | Double up Item 104 |  |  | Unknown |  |  |  | Unknown
126 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 7 | Public standing between the roadside barrier and the rail corridor | Vehicles stopping in an emergency on the State Highway adjacent to the rail corridor | Injury / accident due to being struck by vehicle or slip, trip or fall | Extreme | 4 | Unlikely | 1 | 3 | High | Steve Muller | Roadside barrier to deter access. Inclusion of fencing along road / rail barrier. Additional signage. Increased width of shoulder to improve safety for emergency stopping along highway - unlikely achievable due to spatial constraints. 06/25 need to check against geometric design (s 9(2)(a)) from a cycleway perspective | Extreme | Rare | High | Open | Design Lead Barriers/SH2 Design. Safer operation of SH2. |  |  | Unknown |  |  |  | Unknown
127 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 8 | Operators not sighting signals and stopping. | Location of signals, OLE, and structures causing sighting issues to train operators. | Multiple fatalities | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | KiwiRail Signalling design to meet all sighting standards 06/25 design meets KiwiRail ctandards | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
128 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 11 | Touch potential - overhead lines | Existing Normandale Bridge is not equipped with pedestrian screens. | Injury / Fatality | Extreme | 4 | Likely | 3 | 4 | Critical | Blair Rogers | Bridge screening. 06/25 as confirmed with KiwiRail the track and OLE are not changing under Normandale bridge and screening is not included in scope of work |  |  | Unknown | Cancelled | Requirement for Bridge screening may be triggered from OLE changes, To be reviewed with final OLE design. Risk to be held in register until confirmed. |  |  | Unknown |  |  |  | Unknown
129 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 15 | Hi-rail access and egress may be unsafe - key maintenance requirement for rail | The interface with the existing road and new rail layout. | Injury | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | Hi Rail access will be confirmed and detailed in design with KiwiRail. Good road and rail grades to facilitate direct access. 06/25 design includes best practice access | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
130 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 16 | Slips / trips and falls when train drivers undertake pre departure checks at the stations which involves walking around both sides of the train. | Surrounding environment | Injury from slip / trip / fall | Minor | 1 | Possible | 2 | 2 | Medium | Blair Rogers | Design to ensure area around train to be flat as possible, this is linked to final ballast levels and shaping if needed to ensure level access areas 06/25 Standard station layout adopted in design | Minor | Rare | Low | Open - Managed | Final ballasting to confirm level areas for pre-departure inspection |  |  | Unknown |  |  |  | Unknown
131 |  | West Bank | Rail | Operation | KiwiRail SiD Register - 19 | Errant trains | Insufficient space for the friction buffer stop to perform. | Injuries / fatalities | Severe | 3 | Unlikely | 1 | 2 | Medium | Blair Rogers | Buffer to be designed for train size and speed. 06/25 duplicate of 122, cancel |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
132 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Exposure to high voltage | Member of Public climbs onto traction pole using the fence as a climbing aid. | Electrocution | Extreme | 4 | Unlikely | 1 | 3 | High | Blair Rogers | No foot holds on post to aid climbing. Consider anti climb device where post is less than 1m from fence. Consider signage to warn public of the danger / live voltage where post is less than 1m from fence. 06/25 design maximises distance between fence and pole, all poles approx. 2m | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
133 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Object/Infrastructure from the cycle path onto the tracks. | 1. New fence is located less than 5m from the track centre line (CL). 2. High wind load on fence. 3. Infrastructure (fence) structural failure. 4. Member of Public push over fence. 5. Members of the public throws object on track. | Rail vehicle hits object on track (causes damage to rail vehicle). Object on track punctures rail vehicle and strikes person. Rail vehicle strikes object and derails. | Severe | 3 | Possible | 2 | 3 | High | Blair Rogers | Fence design to withstand high wind load. Fence design to withstand pushing and climbing by Member of Public. Limit new fence height to be less than distance between fence line and rail vehicle (as per National Rail System Standard / 6 Issue 4 Appendix E Line 8/9).Fence poles are to be restrained by fence mesh in design (design to include heavy gauge restraining wire around fence mesh and poles).Consider signage to deter littering / throwing material onto the track with fines quoted. Design includes CCTV to monitor the cycleway 06/25 design maximises distance between fence and pole, all poles approx. 2m | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
134 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Object/Infrastructure from rolling stock into the cycle path | 1. Object falls from rolling stock. 2. Rolling stock pick up an object in the corridor and send it into the cycle path | Object hurts someone in the cycle path | Severe | 3 | Possible | 2 | 3 | High | Blair Rogers | Existing KiwiRail vehicle maintenance. The majority of the project extents runs alongside the Melling line which only carries passenger trains, no freight. 1.8m high fencing in place. Regular maintenance and checking of the fence line and ensure secure. Routine rail corridor and rail vehicle inspections/maintenance. 06/25 O&M manual, construction | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
135 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Derailed train go into the Cycle path | 1. Driver error. 2. Track failure (buckle, twist fault etc). 3. Obstruction on the track. | Derailed train enters cycle path causing possible injuries. Passengers and staff injured | Extreme | 4 | Unlikely | 1 | 3 | High | Blair Rogers | 1. Design maximises clearance between track centreline and fence where possible in this constrained corridor 06/25 - robust kerb incorporated into design for the pinch point area | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
136 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Persons exit train within the rail corridor (&lt;3m-5m instead of 5m clearance). Km1.640 to 2.350 | Train break down or derailment | Drivers/Rail Personnel or members of the public have to exit the train and move along the rail corridor | Moderate | 2 | Rare | 0 | 1 | Low | Blair Rogers | 1. Provision of gates within the fence between the cycle path and the rail corridor (where levels allow) 2. The area between the tracks and the boundary to the cycle path is to be graded suitable for use by foot traffic 06/25 O&M manual, construction | Minor | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
137 |  | West Bank | Rail | Operation | KiwiRail PSHL Rev B | Wire falling down into the cycleway. Include MAD | Derailment. Dewirement with live wires on the ground. Earthquake. Component failure | Fence becomes live with potential for electrocution | Extreme | 4 | Rare | 0 | 3 | High | Blair Rogers | Fault path bonding to be reviewed and confirmed in design. 06/25 any fence in the drop zone will be bonded | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
138 |  | West Bank | Rail / Urban Design & Landscape | Operation | KiwiRail SiD Register - 12 | Movement restrictions in locations where crime is increased due to low level of lighting and CCTV | New arrangement of pedestrian movements | Injury | Severe | 3 | Likely | 3 | 4 | Critical | Blair Rogers | All new public access areas will be reviewed in design to meet lighting standards and adequate levels of CCTV coverage. Full length fencing and lighting to deter trespass. 06/25 As above, CEPTD review to be completed as part of design | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
139 |  | West Bank | Rail / Urban Design & Landscape | Operation | KiwiRail SiD Register - 13 | Rail corridor and fire hydrant access in event of a fire or major public access. | Lack of access. | Injury / Fatality | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | Design to review all requirements for corridor and hydrant access. Potential for cycleway to be used for access, noting the rail corridor now has restricted access with no formed accessway. Street hydrant and fire appliance access to be though through. 06/25 no water connection in cycleway, close |  |  | Unknown | Closed - Eliminated |  |  |  | Unknown |  |  |  | Unknown
140 |  | West Bank | Rail / Urban Design & Landscape | Operation | KiwiRail SiD Register - 14 | Passengers not evacuated quickly enough from the platform(s). | Layout of station, platform and surrounding facilities. | Injury / fatalities. | Extreme | 4 | Likely | 3 | 4 | Critical | Dean Mackenzie | Station egress will be designed to meet all evacuation requirements, along with intermodal and bridge access around the station area. 06/25 fire engineer engaged (s 9(a)(a)) to provide additional advice. note this is a melling station/GWRC matter, not kiwirail | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
141 |  | West Bank | Rail/ Active Modes | Operation | GHD SiD Register - 4 | Conflict between cyclists and pedestrians in mixed use zone around proposed rail station | Poor cyclist / pedestrian provision (pedestrian bridge link over Marsden Street, bus drop off area, parking accesses, etc…) | Injury due to interaction between users | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim /Nicole Thompson | Design to meet all intermodal and bridge access requirements around the station area to reduce risk to different users of the station. 06/25 TBC. note this is a melling station /GWRC matter, not kiwirail | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
142 |  | West Bank | Rail/ Urban Design & Landscape | Operation | workshop 8/08/23 | Relocation of existing Melling Station | Unfamiliarity with new station location presents challenges for vision impaired, mobility impaired, disabled or neurodiverse people. | Accident / injury resulting from trouble navigating new environment | Moderate | 2 | Possible | 2 | 2 | Medium | Dean Mackenzie | Communication with all representative groups during the design process for station layout and operation. Mainly mitigated during initial opening and ongoing assistance at the station. 10/04/25 design includes consultation with several impairment groups, check if also happens immeditate to /just after design. note this is a melling station /GWRC matter, not kiwirail | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
143 |  | River Works | River | Construction | workshop 8/08/23 GHD SiD Register - 53 | Temporary works washed away in flooding | Working within the river channel | Injury to people or damage to property downstream. More work in the river to re-establish. | Severe | 3 | Almost Certain | 4 | 4 | Critical | Matt Fairweather | Design temporary works for 1:100 year flood. (THIS SOUNDS QUITE HIGH) Allow for aggregate causeway to be able to wash away allowing for more river channel capacity in flood event, therefore protecting remaining temp works. Carry out hydraulic modelling of river channel with Temp works arrangement to understand risk. Flood response plan to be developed. | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
144 |  | River Works | River | Construction | workshop 8/08/23 GHD SiD Register - 51 | Falling into the water | Construction of infrastructure within the river channel, such as rip rap, Urunga, bridges, stopbanks / berms, landscaping at river edge | Drowning, accident, injury. | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Taylor | Minimise river works required for design. Training on river safety. Modular design to avoid working on river. Sequencing model. Try to ensure more mechanical work than manual. Public wayfinding design for legibility even during operation. Public exclusion during construction. Extend life of systems to reduce need for maintenance. | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
145 |  | River Works | River | Construction/ Maintenance | GHD SiD Register - 55 | Excavating river gravels | Working in the river | Drowning, accident or injury | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Taylor | SOP, consent conditions. Piles close to river bank - design to reduce need works in the river. Flood response plan. Training e.g. wader courses for fish salvage. Bigger plant. Working in the beach as much as possible. Response training. Capability assessment. | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
146 |  | River Works | River | Maintenance | GHD SiD Register - 64 | Infrastructure getting in the way of maintenance vehicles in flood response activities | Maintenance access limited by infrastructure such as lighting columns, furniture, signs etc. | Delayed flood response | Moderate | 2 | Possible | 2 | 2 | Medium | Swaraj Baral | Design in redundancy to provide access from landside of stopbanks, Clearance envelope in shared path in an emergency for use. 04/25 - design incorporates best practice, ongoing liaison with relevant asset owners 06/08/2025 PC - N/A Captured in GWRC river corridor design | Moderate | Possible | Medium | Cancelled |  |  |  | Unknown |  |  |  | Unknown
147 |  | River Works | River | Operation | workshop 8/08/23 | Flood damage risk from lower berm accessibility | Lower berm accessibility with new alignment | Accident / injury / death due to being caught in flood | Extreme | 4 | Unlikely | 1 | 3 | High | Andrew Craig | Limited potential to change elevations or frequency of wetting. Work with contractor to streamline construction methods and exposure. Warning sign visual. Boom for carparks to limit access. Signage around flooding zones. Digital signage/EMS to provide advance warning. Flood evacuation route signage? Audio signal to evacuate? 04/25 - construction team to liaise with other contractors undertaking work that could impact alliance work | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
148 | Y | River Works | River | Operation | workshop 8/08/23 | Flood gates at outlets | debris enters SW system and blocks outlet |  | Severe | 3 | Possible | 2 | 3 | High | Diana Dumitrascu | Flap stop to hold debris. Penstocks - better to remove need for people to go in during flood event. 04/25 - design incorporates best practice including limiting opportunity for debris to enter SW system | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
149 | Y | River Works | River | Operation | workshop 8/08/23 | Isolation of Riverbank pathways after maturity of trees (CPTED) | [6 empty] | No | Unknown | Nicole Thompson | CPTED audit of design 04/25 - cancelled, now out of scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
150 |  | River Works | River | Operation | workshop 8/08/23 | Whole of life elements of River installation | Maintenance activities? (this was not populated) | Accident / injury / death due to being caught in flood or after flood clearing debris etc | Extreme | 4 | Unlikely | 1 | 3 | High | Andrew Craig | Safe maintenance practices for Alliance, and for GW post Alliance. SOP, consent conditions. Piles close to river bank - design to reduce need works in the river. Flood response plan. Training e.g. wader courses for fish salvage. Bigger plant. Working in the beach as much as possible. Response training. Capability assessment. 04/25 - design incorporates as much as practicable. balance to construction team, O&M manual? | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
151 |  | River Works | River | Operation | GHD SiD Register - 10 | Flood risk (GW and Alliance) | Movement of river channel exacerbating bank erosion | Increased flood risk | Severe | 3 | Rare | 0 | 1 | Low | Andrew Craig | Additional bank protection, inspection &amp; maintenance. Coordination required. Reinstatement post alliance e.g. temporary state after alliance work e.g. rock stability. River monitoring. | Severe | Rare | Low | Cancelled |  |  |  | Unknown |  |  |  | Unknown
152 | Y | River Works | River/ Urban Design & Landscape | Operation | GHD SiD Register - 20 | Unsafe user behaviour | Vacating carpark with flood coming | People stuck in the way of the flood (noting this is a current risk) | Extreme | 4 | Rare | 0 | 3 | High | Nicole Thompson | Wayfinding, SOP, technology (e.g. text messaging warnings). Signage. Repositioning of carpark. Egress capacity. One way barrier to allow egress. Warning sign visual. Boom for carparks to limit access. Signage around flooding zones. Digital signage/EMS to provide advance warning. Flood evacuation route signage? Audio signal to evacuate? 06/25 - HCC, removed from alliance scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
153 |  | River Works | River | Natural Disaster | workshop 8/08/23 | Risk to public within flood protection area | Impacts to existing stopbank changing flood protection area | Accident / injury / death due to being caught in flood | Extreme | 4 | Rare | 0 | 3 | High | Andrew Craig | Signs and potentially automated barriers to vehicle entry. Wayfinding, SOP, technology (e.g. text messaging warnings). Signage. Repositioning of carpark. Egress capacity. One way barrier to allow egress. Warning sign visual. Boom for carparks to limit access. Signage around flooding zones. Digital signage/EMS to provide advance warning. Flood evacuation route signage? Audio signal to evacuate? |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
154 |  | River Works | River | Operation | workshop 8/08/23 | Natural Disaster - Large debris floating down the river, particularly for temporary works. | Flood or other weather event depositing large debris in the river | Accident / injury / death. Damage to structures in the river | Extreme | 4 | Rare | 0 | 3 | High | Matt Fairweather | Stick to minimum requirements (soffit clearance), maximise bridge spans, minimise piers, consider pier shape. Rip-rap to protect structure where possible to reduce disruptions. Regular inspection and maintenance of temporary works areas. Use CCTV to clear debris before it becomes an issue, e.g. on bridges. Design temporary works to consider flood risk. | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
155 |  | River Works | River | Operation | TAN-0066 | Natural Disaster - Unprepared for flood event during construction. | Insufficient river / stopbank monitoring | Accident / injury / death due to flooding impacts | Extreme | 4 | Unlikely | 1 | 3 | High | Matt Fairweather | Signs and potentially automated barriers to vehicle entry (see 147). Flood response plan. Catchment monitoring/forecasting. Warning system. | Severe | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
156 |  | Project Wide | Stopbanks | Construction | SiD workshop 07/09/23 | Deep excavations. | Deep cut-off trench for stopbanks. Unstable ground. | Trench collapse leading to injury or death. | Extreme | 4 | Possible | 2 | 4 | Critical | Russell Allison/ Omar Issadeen | Use different trench design with bentonite trench or no trench. liaise with construction team to develop a design that minimises construction risk. Primarily a construction risk | Extreme | Rare | High | Construction | Battering back trench. People only in plant, not entering trench. |  |  | Unknown |  |  |  | Unknown
157 |  | Project Wide | Stopbanks | Construction | TAN-0066 | Unsafe operation of crane | Crane required for stopbank construction. Unstable/sloping ground. | Accident / injury / death associated with working in / around crane | Extreme | 4 | Possible | 2 | 4 | Critical | Matt Fairweather | Consider construction sequence in design to minimise crane access. Include contractor in design options. Cranage laydown area provided. Temporary works to include purpose built crane platform(s) Primarily a construction risk | Moderate | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
158 | Y | Project Wide | Stopbanks | Maintenance | TAN-0066 | Stopbank maintenance | Constrained access to stopbank off local road | Accident / injury / death due to traffic accident | Extreme | 4 | Possible | 2 | 4 | Critical | Omar Issadeen | Maximise available access points for safety. Provide suitable minimised maintenance. Include maintenance requirements in design. Design in redundancy to provide access from landside of stopbanks, Clearance envelope in shared path in an emergency for use. |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
159 | Y | Project Wide | Stopbanks | Operation | TAN-0063 | Fall from stopbank/down batter slope | Height and slope of batter slopes in relation to active mode users safety | Accident / injury to shared path user. | Moderate | 2 | Likely | 3 | 3 | High | Omar Issadeen | Handrails / barriers. Flattening of batters. Accessibility for all users. 04/25 - design to include best practice 06/08/2025 PC - Batter slope assessment undertaken. Widen edge detail with pedestrian handrail, where provided, to minimise of injury. Ongoing | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
160 | Y | Project Wide | Stopbanks | Operation | GHD SiD Register - 27 | Public access rock lining and climb down them. | Unsafe user behaviour | Accident / injury. | Moderate | 2 | Possible | 2 | 2 | Medium | Omar Issadeen | Legible paths. Good signage. 04/25 - design to include best practices | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
161 | Y | Project Wide | Stopbanks | Natural Disaster | TAN-0066 | Electrical infrastructure around stopbanks | Interaction between stopbanks and electrical infrastructure on site including transformers. | Accident / injury / death due to water interaction with electrical assets during flood event | Extreme | 4 | Possible | 2 | 4 | Critical | Graeme Doherty | Locate land side where possible Design to include measures that minimise or eliminate risk |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
162 | Y | Project Wide | Stormwater | Construction | TAN-0106 | Very deep excavation for pump wells for pump station - constrained space, ground water | Deep wells to accommodate pump suction head and operational requirements. | Excavation collapse, water ingress impacting person or plant. | Extreme | 4 | Likely | 3 | 4 | Critical | Abby Carolan | Ensure access for personnel design for safe access and work. Fewer pump stations included. Design temporary works 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
163 | Y | Project Wide | Stormwater | Construction | TAN-0066 | Pump station construction | Each pump station is a large, below ground structure | Accident / injury / death associated with construction of stopbanks | Extreme | 4 | Possible | 2 | 4 | Critical | Abby Carolan | Don&#39;t put underground. Minimise below ground. Locate within bigger area. Use prefabricated pump station. Remove pumpstation all together. From TAN-0066: Construction safety will be considered in conjunction with the structural design during subsequent design phases including the following: -Deep excavation with likely requirement for shoring / sheet pile reinforcements due to spatial requirements -Water ingress -Existing services -Undermining of adjacent structures 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
164 | Y | Project Wide | Stormwater | Maintenance | TAN-0066 | Pumpstation location | Difficulty accessing pumpstation location for construction, operation and maintenance | Injury due to traffic accident. Delays in accessing pump station due to traffic management requirements. | Moderate | 2 | Likely | 3 | 3 | High | Abby Carolan | Located pumpstations outside of roadways to reduce interface with traffic during construction, operation and decommissioning. Could eliminate pumpstations altogether 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
165 | Y | Project Wide | Stormwater | Maintenance | TAN-0066 | Raking of bar screens at each pump station without entry to the wet well. | Raking of bar screens will be performed by operators standing on top of the pump station with fall restraint. The maximum height of manually raked screens in accordance with EM-1110-2-3105 is 6.0m and mechanical screens may therefore be required based on the current design depths. | Injury or death caused by undertaking of maintenance activities. | Extreme | 4 | Likely | 3 | 4 | Critical | Abby Carolan | Design for less access. Above ground design. Off shelf design. Automated cleaning maintenance. The provision of handrails or other safety measures may be considered, as well as provision of screening up stream of the pump station within the drainage network. 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
166 | Y | Project Wide | Stormwater | Maintenance | TAN-0106 | Fall from height during maintenance of pump station | Maintenance required in pump well | Accident / injury | Severe | 3 | Possible | 2 | 3 | High | Abby Carolan | Remove pump stations. From TAN-106: safety access grates, anchor points, mounting points for retrieval., Designed so pumps can be removed without having to access bottom of the well (have minimised anything in the bottom of the well that need regular maintenance). design assumes that raking of bar screens at pump stations will be carried out without accessing the wet well. Assumed to be performed by operators standing on top of the pump station with fall restraint. The provision of handrails or other safety measures may be considered through the SiD process 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
167 | Y | Project Wide | Stormwater | Maintenance | workshop 8/08/23 | Pump station outlet access | People accessing pump station outlet (2m diameter) | Injury / death due to heat, gases, drowning. | Extreme | 4 | Possible | 2 | 4 | Critical | Abby Carolan | Remove pump stations 06/25 - pumps removed from design/scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
168 | Y | Project Wide | Stormwater | Construction/<br>Operation | workshop 8/08/23 | Stormwater assets | Damage to stormwater assets due to settlement | Damage to assets leading to blockages, flooding. | Moderate | 2 | Possible | 2 | 2 | Medium | Diana Dumitrascu | Adequate bedding. Settlement assessment. 06/25 - design includes best practice, residual risk to Wellington Water. Settlement and potential pipe leaks through stop banks, HDPE pipe minimises risk. | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
169 | Y | Project Wide | Stormwater | Maintenance | workshop 8/08/23 | Stormwater chamber / pit locations. Median drainage on the interchange. | Maintenance activities in / beside carriageway - errant vehicle enters closure. | Injury or possible death from traffic accident. | Extreme | 4 | Likely | 3 | 4 | Critical | Diana Dumitrascu | Move chambers to safter locations, i.e. footways. Review materials and design for less maintenance. Maintenance. 06/25 - moved to safer location where possible. move to construction, O&M manual | Extreme | Rare | High | Construction | O&M manuals to include requirements |  |  | Unknown |  |  |  | Unknown
170 | Y | Project Wide | Stormwater | Maintenance | workshop 8/08/23 | Overflow of retaining wall drains | Drains on top of retaining walls difficult to maintain due - particularly western hill areas | Overflow of drains causes accident / injury | Moderate | 2 | Likely | 3 | 3 | High | Diana Dumitrascu | Design / select materials for less maintenance. Integrate fall protection in design. Design drains out, consider if they are needed Reduced drains required (mitigated). 06/25 - duplicate of other item(s). |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
171 | Y | Project Wide | Stormwater | Maintenance | TAN-0066 | Working in confined space to undertake maintenance activities. Sufficient size of chambers and lids. McBernss safety lids where possible. | Entry of pump well, valve pit and backflow prevention pits for access to valves and pumps etc | Worker overcome by gases or heat. Injury, death. | Extreme | 4 | Likely | 3 | 4 | Critical | Diana Dumitrascu | Siting access. Lifting material out instead of people going inside. Plug and play design (less people). Design ventilation into permanent works. From TAN-0066: All maintenance activities associated with the pumps will be performed without entry to the wet well. The main axial flow pumps are to be lifted out of their casings for inspection or maintenance. Similarly, the smaller centrifugal sump pumps are to be installed on rails allowing them to be lifted from above for removal and reinstatement. Large removable McBerns safety covers provided. Non-trafficable variant specified to reduce lifting weights. Mounting plates for removable davit arms provided Pipework / valves in valve chamber made as shallow as possible Double isolation not currently provided and may be required following consultation with the Asset Owner (Wellington Water) Residual risk - confined space and working at heights is assumed to be restricted and managed by operations as a confined space. Further consultation with the Asset Owner is required. Bench surface for safety lid. 06/25 - design allows for as much as possible to minimise residual risk | Extreme | Rare | High | Construction | O&M manuals to include requirements |  |  | Unknown |  |  |  | Unknown
172 | Y | Project Wide | Stormwater | Maintenance | workshop 8/08/23 | Cleaning debris screens | Manual cleaning of debris screens with depth up to 6m. | Injury / death from fall, heat, gases, drowning. | Extreme | 4 | Possible | 2 | 4 | Critical | Diana Dumitrascu | Remove pump stations 06/25 - pumps removed from scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
173 | Y | Project Wide | Stormwater | Maintenance | TAN-0122 | Maintenance within confined space | Stormwater scupper/catch pits and pipes within the bridge structure | Injury / death due to being trapped or collision with live traffic | Extreme | 4 | Possible | 2 | 4 | Critical | Diana Dumitrascu | Self cleaning materials. Smaller pipes. Locate pipes. Make bridge steeper so no need for confined access. 06/25 - design incorporates as much as practicable to minimise residual risk. | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
174 | Y | Project Wide | Stormwater | Maintenance | SiD workshop 07/09/23 | Cleaning / flushing of sumps, lamp holes etc. | located in positions within or adjacent to live traffic | Injury / death due to being trapped or collision with live traffic | Extreme | 4 | Possible | 2 | 4 | Critical | Diana Dumitrascu | 06/25 - design incorporates as much as practicable e.g. physical access availability, shoulder widths, locate sumps near car parks where possible etc. | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
175 | Y | Project Wide | Stormwater | Operation | workshop 8/08/23 | Garden bed edges / Passive irrigation | Lack of warning / delineation between path and rain garden | Path users particularly blind / vision impaired and mobility impaired slip / trip / fall causing injury | Moderate | 2 | Possible | 2 | 2 | Medium | Diana Dumitrascu | Provision of 0.5 m edge of vegetation to avoid slips. 06/25 - no rain gardens in design | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
176 |  | Project Wide | Stormwater | Operation | TAN-0066 | Dry side location of penstocks for stopbank drainage | cyclist risk due to location adjacent to shared path | Path users particularly blind / vision impaired and mobility impaired slip / trip / fall causing injury | Moderate | 2 | Likely | 3 | 3 | High | Diana Dumitrascu | 06/25 - Risk mitigated by provision of above ground spindle, cover above ground. Is however located adjacent to a shared path, need to make sure OK from cycle safety 06/08/2025 PC - N/A Penstock moved off shared path. | Moderate | Rare | Low | Cancelled |  |  |  | Unknown |  |  |  | Unknown
177 | Y | Project Wide | Stormwater | Operation | TAN-0066 | Wet side location of penstocks for stopbank drainage | Limited access to wet side penstock during flood event | Accident / injury / death trying to access penstock during flood event or becoming trapped in drainage system | Extreme | 4 | Possible | 2 | 4 | Critical | Diana Dumitrascu | Move penstocks out of wet area during design. Appropriate temporary works 06/25 - no wet side penstocks | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
178 | Y | Project Wide | Stormwater | Operation | TAN-0106 | Public access to drainage structures | Insufficient security provisions to prevent public accessing drainage structures | Injury / death from being trapped, heat, drowning | Extreme | 4 | Likely | 3 | 4 | Critical | Diana Dumitrascu | Grills over the pipes (consider maintenance implications), multiple smaller diameter pipes instead of one large one. Manhole keys. Flap gate (but this would create a new hazard for maintenance access and silt build up) 06/25 - design incorporates as much as practicable including flap gates to outlets, scruffy domes in largely inaccessible areas. On going project wide review | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
179 | Y | Project Wide | Stormwater | Operation | TGDD SiD Register - 38 | Stormwater runoff spilling onto or flowing across carriageway. Increased water film depth resulting in aqua planning causing vehicle accident | Flows in excess of design capacity due to large rainfall event or blockage | Injury or possible death caused by accident | Severe | 3 | Possible | 2 | 3 | High | Diana Dumitrascu | Review design storm and provide freeboard in design. Consider climate change in design events/ flows 04/25 - design incorporates as much as practicable. Designed for areas of film flow, partial blockage of system, all as per guidelines and design standards. Asset owner to cover any residual risks eg flat longitudinal areas. Transfer to construction (O&M manual?) | Moderate | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
180 | Y | Project Wide | Stormwater | Natural Disaster | workshop 8/08/23 | Significant surface water flow (runoff) at top of wall | Drains on top of retaining walls - particularly western hill areas on top of retaining walls undersized | Overflow of drains causes flooding, accident / injury to active mode users below | Moderate | 2 | Likely | 3 | 3 | High | Diana Dumitrascu | Review storm water modelling and upsize. Move the overflow drains. Redirect design for secondary flows. Challenge if we need this drainage. 06/25 - design incorporating as/where required e.g. catch drains on top of walls. Conc dish channel, low maint. Need to check self cleaning velocities. Where required, fall protection to be considered 06/08/2025 PC - Design analysis. Ongoing | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
181 | Y | Project Wide | Stormwater | Natural Disaster | workshop 8/08/23 | Stormwater chamber / pit locations | Insufficient maintenance carried out due to difficulty accessing chambers / pits. | Flooding due to exceedance of network capacity. | Moderate | 2 | Almost Certain | 4 | 3 | High | Diana Dumitrascu | Provide access to pit locations. Maintenance regime 06/25 - design incorporates as much as practicable. Ongoing design review to optimise | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
182 |  | River Works | Structures | Construction | workshop 8/08/23 | Access to temporary casings when piling in the river | Temporary casings required for aquifer protection | Accident / injury / death trying to get access for temporary casings when piling in the river | Extreme | 4 | Likely | 3 | 4 | Critical | Kelsy Seyb | Don&#39;t put people in this situation. Change design to shallow / foundation. Reduce no. of piers with larger spans. The platform piling method negates outer caisson. Alternate methodology in progress. 07/25 - design minimises but still piled foundations, oversize sleeves, casings caissons, mitigation measures to avoid having to send people down caissons | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
183 |  | River Works | Structures | Construction | TAN-0101 | Personnel and plant working within live river channel | Unexpected response from temporary structure or partially built structural elements | Safety and environmental risk around people, materials, plant, debris falling into water, and a risk around limited ability for access / egress at a work front. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Temp works designed to 1:100 AEP. Hydraulic model of river channel to included temporary works sequence. Staged design to reflect kinematic response to temporary works stages. FMP &amp; monitoring of flows. Work behind bonds. Design bridge not to be in river channel as much as possible 1:100 TEMPORARY WORKS A HIGH STANDARD 07/25 - temp works design, construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
184 |  | Project Wide | Structures | Construction | GHD SiD Register - 52 | Unsafe operation of crane (ground conditions) | Cranes required to operate from sloping ground / unstable river bank for bridge construction | Plant rollover, injury / death, damage to structure | Extreme | 4 | Likely | 3 | 4 | Critical | Kelsy Seyb | Construction method is off crane platforms / causeway or staging. Qualified and experienced operators i.e. know not to operate on sloping ground. 07/25 - temp works, construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
185 |  | Project Wide | Structures | Construction | TAN-0101 SiD workshop 07/09/23 | Falls from height during construction | Construction of bridges. Temporary formwork to bridges. | Injury / death due to fall from height | Extreme | 4 | Likely | 3 | 4 | Critical | Kelsy Seyb | Temp works to consider edge protection. These are in place prior to working at height (i.e. on beams before lifted in). Permanent formwork. Edge protection with design for deck. 07/25 - transfer to construction team, temp works, liaise with construction for permanent edge protection designed to be installed where possible to minimise temp protection | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
186 |  | Project Wide | Structures | Construction | TAN-0104 | Falls from height during construction | Naturally some need for work at height in order to build the retaining walls. Also working in vicinity of existing walls, up to circ 3m high | Injury/accident | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Cut face RW use spec. sub qualified in rope access or work off manage with crane. Reduce slope angle if possible. Integrate edge protection into RW design. Eliminate RW where possible. L wall design lifting eye which can accommodate a release clip from ground level. Scope of cut slopes reduced. 07/25 - transfer to construction team, temp works, liaise with construction for permanent edge protection designed to be installed where possible to minimise temp protection | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
187 |  | Project Wide | Structures | Construction | TAN-0150 | Fall from existing retaining walls during construction | Working in the vicinity of private land with retaining structures on the boundary. Some walls are approx. 3.0m high. | Accident / injury / death due to fall from height | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Design temp edge protection . Investigate if RW can remain and be buried 07/25 included in 186 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
188 |  | Project Wide | Structures | Construction | workshop 8/08/23 | Earthquake risk during bridge construction | Earthquake occurs during construction of bridges | Accident / injury / death due to bridge collapse, or debris from damaged infrastructure | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Temp works designed to 1 in 100 return period. Designers to assess permanent works based on the construction sequence. Temp works seismic consideration. 07/25 - temp works design, egress routes etc. transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
189 |  | Bridges | Structures | Construction | workshop 8/08/23 | Te Awa Kairangi Pedestrian Bridge washing away during construction | Te Awa Kairangi Pedestrian Bridge more susceptible to washing away before construction complete | Accident / injury / death due to debris from bridge | Extreme | 4 | Unlikely | 1 | 3 | High | Kelsy Seyb | No towers in the river corridor. Constructing directly on piers - risk lower due to height. 07/25 work now excluded from scope (HCC) |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
190 |  | Project Wide | Structures | Construction | workshop 8/08/23 | Bridge construction methodology | Construction methodology makes bridges more susceptible to failure during construction if extreme weather event occurs | Accident / injury / death due to bridge collapse, or debris from damaged infrastructure | Extreme | 4 | Unlikely | 1 | 3 | High | Kelsy Seyb | Design out as far as possible needed to build a bridge in river channel (i.e. Network Arch) 07/25 - as above, design includes max spans etc | Moderate | Rare | Low | Closed |  |  |  | Unknown |  |  |  | Unknown
191 |  | Bridges | Structures | Construction | workshop 8/08/23 | Deconstruction of existing Melling Bridge. | Difficulty deconstructing existing Melling bridge due to its structural form. | Collapse of works which result in failed material impacting person or plant causing serious injury or possibly death | Extreme | 4 | Rare | 0 | 3 | High |  | Sequence plan identified. 07/25 - transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
192 |  | Project Wide | Structures | Construction | GHD SiD Register - 48 | Working in a constrained environment | MSE wall stability may be compromised during construction due to constrained construction site, in particular around the Melling Interchange | Accident / injury | Severe | 3 | Possible | 2 | 3 | High | Kelsy Seyb | Constructor needs the wall to be designed to a lower depth on west abutment to accommodate construction sequence. Design all assets together 07/25 design optimises space but remains limited. transfer to construction team | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
193 |  | Bridges | Structures | Construction | TGDD SiD Register - 99 | Overloading bridges during construction | Stacking material using cranes, trucks, graders or other construction equipment on bridge and overloading when element not designed to take load, plant or vehicle | Injury/death or damage/collapse of element | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Allowing for construction loading in design Coordination with construction to understand what plant/ equipment to be used during construction Consider different stages of construction in design Communicating limits of design to constructors, i.e. indicating on drawings, especially locations where load should not be places during construction. 07/25 transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
194 |  | Bridges | Structures | Construction | TGDD SiD Register - 292 | Construction team adopting different construction requirements and methodology or sequencing to that assumed in the design. | Incorrect assumptions or inadequate information | Injury/death or damage/collapse of element | Extreme | 4 | Unlikely | 1 | 3 | High | Kelsy Seyb/ Matt Fairweather | Coordinate with contractor. Construction execution plan reviewed by designers. 07/25 ongoing liaison with construction team to coordinate etc. | Severe | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
195a |  | Bridges | Structures | Construction | SiD workshop 07/09/23 | Tight confined spaces producing challenges for steel fixing and bearing installation | Insufficient space for complex rebar and built in items | Injury to steel fixers or carpenters. Quality issues | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Prefabricate. Use alternatives to reinforcement. Post-tensioning. 07/25 will be looked at more as design progresses including reinforcement detailing, post tension design, etc. | Severe | Unlikely | Medium | Open | Prefabricate |  |  | Unknown |  |  |  | Unknown
196 |  | West Bank | Geotechnical | Construction | SiD workshop 07/09/23 | Rockfall / instability causes harm to construction personnel who can't get away as the live SH2 is behind them | Dislodged rock fragments or larger rocks as faces are cut / prepared for rock bolts / profiling. Hurt people or damage adjacent areas / property | Injury/death | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller/ Russell Allison | Reduce amount of work on cut slopes. Re-use existing roading / slopes retained &quot;as-is&quot; wherever possible. Temporary works as required. Alignment realigned to minimise works 09/04/25 Above incorporated into design wherever practicable |  |  | Unknown | Construction | Limit work zones to provide egress opportunities at all times |  |  | Unknown |  |  |  | Unknown
197a |  | River Works | Structures/ Geotechnical | Construction | TAN-0101 | Piling work negatively impacting the integrity of the Waiwhetu Aquifer | Piling required in river | Waiwhetu aquifer supplies a significant portion of public freshwater supply, so contamination / depressurisation could have significant health impacts | Severe | 3 | Almost Certain | 4 | 4 | Critical | Kelsy Seyb/Russell Allison | Move ground investigations in river. To support understanding of Aquatard level and thickness. Look into risk of shallow vs. piles). Reduce no. of piers. Do not pile in aquifer? From TAN-101: Subsurface work with aquifer interfaces has been completed in the Hutt Valley previously – at Ewen Bridge, various water bores, investigative boreholes etc. The piling methodology will be prepared with consideration of lessons from the past, and can draw upon input from those involved in successful management of the aquifer in these prior activities. 09/04/25 alternate piling methodology (GWRC approved in principle) that reduces risk of likelihood. Final approval TBC. construction risk also | Severe | Possible | High | Open |  |  |  | Unknown |  |  |  | Unknown
198 |  | Project Wide | Structures / Geometrics | Construction/ Operation | workshop 8/08/23 | Impact / collision with retaining walls | Alignment / geometry of road and wall, vehicle operator error | Accident / injury / death. Damage to asset. Closure of road(s) / SH2 to allow for repairs. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb/ Steve Muller | Best practice design. Snagging pocketing removed (operational). For construction protect against head on impact, consider in staging. Bigger stages means less moves. 07/25 Barriers integrated, ongoing. | Extreme | Rare | High | Open |  |  |  | Unknown |  |  |  | Unknown
199 | Y | Bridges | Structures | Maintenance | TAN-0101 | Fall from height while performing structures maintenance | Maintenance activity required at pierheads. Using anchors/walkways/platforms designed into structures. | Accident / injury / death Human error Systemic failure due to emergency | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Fence backstreets, provide fall protection at vertical retaining walls. Also underpasses. Cast in fall restraint anchors / design platform = Alliance provide system. Design aprons in the seating / overlap area at piers, bankseats to allow for robotic wheeled access for remote inspection. Design for remote/drone/robot (provision) inspection over human. 07/25 now excluded from scope (HCC) |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
200 | Y | Bridges | Structures | Maintenance | workshop 8/08/23 | Bridge maintenance around active mode users | Ongoing bridge maintenance and replacement | Accident / injury due to collision between construction workers and active mode users | Moderate | 2 | Possible | 2 | 2 | Medium | Kelsy Seyb | 07/25 ongoing, access typically from SH2 and elsewhere, space on ramps for maintenance vehicle parking, O&M manual 06/08/2025 PC - New Melling River bridge - use of bucket to access under bridge will require TM/lane closure with narrow lanes to accommodate active mode users. HCC responsible for bridge - refer to separate HCC SiD session. Bollard design impact on access to be assessed. Potential Departure required for access with bollards. Interchange bridge access from SH2. Ongoing. | Moderate | Possible | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
201 |  | Bridges | Structures | Maintenance | SiD workshop 07/09/23 | Inspection and repairs of bridges post seismic event, flood event or strike. | Damage requiring inspection and repair. Inspection involves confined spaces, working at heights, live corridor or over water. Risk of collapse of structure during inspection or repair. | Injury or death. | Extreme | 4 | Rare | 0 | 3 | High | Kelsy Seyb | Consider elements likely to be damaged in seismic event and the ability to inspect and repair - scenario testing. Minimise exposure duration and simplify access and false work connections. Design in connection points to piers and abutments. E.g. through holes which can be used to clamp platforms and falsework at a later date. 07/25 ongoing, design includes risk reduction elements where practicable 06/08/2025 PC - Design development to be based on agreed Importance Level (IL). Ongoing | Extreme | Rare | High | Open |  |  |  | Unknown |  |  |  | Unknown
202 |  | Project Wide | Structures | Operation | GHD SiD register - 23 | Bridges are not fit for purpose in 100 years time | Damwatch future state modelling review of earlier T+T modelling informing stopbank levels and bridge clearance requirements | Failure of bridge structure. Additional construction / maintenance work | Moderate | 2 | Possible | 2 | 2 | Medium | Kelsy Seyb | 07/25 canceled as design based on GWRC requirements, out of project scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
203 |  | River Works | Structures | Operation | GHD SiD Register - 21 | Work at depth below the river | Bridge piles need to be cut 5m below bed level | Accident / injury | Severe | 3 | Likely | 3 | 4 | Critical | Kelsy Seyb | Challenge consent on 5m. Raise to practicable cut off level (keep columns and future cycle connections). Primarily constructability risk 07/25 5m reduced to 2m, construction team | Severe | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
204 | Y | Bridges | Structures | Operation | workshop 8/08/23 | Unsafe user behaviour on and around bridges | Ease of access to bridges, climbing on handrails - insufficient barriers / rails / screens | Suicide / harm from jumping off bridge. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | On SH2 anti-throw / climb screens. Assess historical data, get understanding of risk, allow for retrofit of screens / mesh etc. for new Melling & pedestrian bridges. Anticlimb provision 07/25 MR's only require for SH2, balance out of project scope. Assessment to be completed during design and installed if required 06/08/2025 PC - Best practice design. No screens to be provided. Ongoing | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
205 | Y | Bridges | Structures | Operation | workshop 8/08/23 | Unsafe user behaviour on and around bridges | Ease of access to bridges, insufficient barriers / rails / screens | People throwing items off the bridge causes traffic accident. | Severe | 3 | Likely | 3 | 4 | Critical | Kelsy Seyb | Anti-throw screens. See 128, carry out risk assessment (maybe QLD DTMR guidelines) 07/25 MR's only require for SH2, balance out of project scope. Assessment to be completed during design and installed if required 06/08/2025 PC - Assessment undertaken to be captured in development. Ongoing | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
206 | Y | Project Wide | Structures | Operation | workshop 8/08/23 TAN-140 | Unsafe user behaviour on and around retaining walls | Ease of access to edge of retaining wall, insufficient barriers / rails | Accident / injury / death from falling from retaining wall | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Fencing in generally public access areas (pedestrians). Barriers should suffice in other locations / retrofit access 07/25 - duplicate of 029, close |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
207 | Y | Project Wide | Structures | Operation | workshop 8/08/23 | Unsafe user behaviour on and around retaining walls | Ease of access to edge of retaining wall, insufficient barriers / rails | People throwing items off the retaining wall causing harm to active mode or road users below | Severe | 3 | Likely | 3 | 4 | Critical | Kelsy Seyb | Compare local structure where required for similar solutions. Prevent access where practicable. Lighting and limit throwable items where possible 07/25 - duplicate of 029, close |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
208 | Y | West Bank | Structures / Geometrics | Operation | workshop 8/08/23 | Impact / collision with pier on SH2 bridge | Alignment / geometry of road and bridge, vehicle operator error | Accident / injury / death. Damage to asset. Closure of road(s) / SH2 to allow for repairs. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb/ Steve Muller | Single span bridge. Pier designed out 07/25 pier designed out, close |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
209 | Y | Project Wide | Structures / Geometrics | Operation | workshop 8/08/23 | Impact / collision with new Melling River Bridge | Alignment / geometry of road and bridge, vehicle operator error | Accident / injury / death. Damage to asset. Closure of road(s) / SH2 to allow for repairs. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb/ Steve Muller | Edge borders. Continuous Design to meet applicable design standards 07/25 - design solution being developed for cantilever path on south side of bridge 06/08/2025 PC - Bollard provision on western side of New Melling River bridge to accommodate pedestrian movements and allow vehicle. Departure to be sought based on agreed design tbc with HCC. Ongoing | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
210 | Y | West Bank | Structures / Geometrics | Operation | workshop 8/08/23 | Impact / collision with gantry supports | Placement of gantries, vehicle operator error | Accident / injury / death. Damage to asset. Closure of road(s) / SH2 to allow for repairs. | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb/ Steve Muller | Per 126, appropriate barrier design and positioning of gantry vertical elements. Complete double carriageway spam. 07/25 - 7 gantries will be protected by barriers or be located where unable to be hit by vehicles 06/08/2025 PC - Deflection zones assessed and gantries relocated accordingly. Sightlines also assessed. Ongoing | Severe | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
211 | Y | Project Wide | Geometrics | Operation | TAN-0101 | Wheeled vehicles (cyclists, pushchairs etc.) on path come off the bridge at high speed or with limited control over deceleration. | Longitudinal fall on the bridge which is accentuated at each end. | Accident / injury due to inability to stop or slow down when coming off bridge | Severe | 3 | Likely | 3 | 4 | Critical | Kelsy Seyb/ Steve Muller | Surface treatment, signage and good sight distance. Grade pedestrian / cyclist path at differing fall to road carriageway 04/25 design looking at options to address any areas of concern across project. e.g. Signage (speed limit), cycle path calming measures (chicane) / speed bumps 06/08/2025 PC - Gradient of paths as high as 8% (4 & 6% in locations) have been refined where practical. Gradients to be further mitigated where possible through the design. Ongoing | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
212 | Y | Project Wide | Structures/ Geometrics | Operation | GHD SiD Register - 5 | Poor cyclist / pedestrian provision leading to injury | High cycle speed coming downhill off the bridge into the Rutherford / Queens intersection with users not able to take the corner safely (linked to Harvey Norman access) | Accident / injury | Severe | 3 | Possible | 2 | 3 | High | Kelsy Seyb/ Steve Muller/ Mike Pilgrim | Signage (speed limit), cycle path calming measures (chicane) / speed bumps 04/25 - duplicate of 211 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
213 | Y | Project Wide | Structures/ Urban Design | Operation | TGDD SiD Register - 168 SiD Workshop 07/09/23 | Safe use of underpasses | No lighting to underpasses. Creates security and safety issues. Visibility issue for users of underpass. | Increased fear of crime leading to reduced usage. Injury, death from collision. | Extreme | 4 | Possible | 2 | 4 | Critical | Nicole Thompson | Add lighting opportunities for natural light Review dimensions for design, tapered entrances to improve natural light/ CPTED 04/25 - no underpassess in scope anymore, cancel |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
214 |  | West Bank | Structures/ Rail | Operation | GHD SiD Register - 39 KiwiRail SiD Register - 6 | Pier strike by train | Movement of rail closer to Normandale bridge pier. The existing pier at Normandale bridge is not designed to be impacted by a train. | Accident / injury / death. Bridge damage/ bridge collapse. | Severe | 3 | Unlikely | 1 | 2 | Medium | Kelsy Seyb/ Blair Rogers | 06/25 not in scope, track remain in current position under Normandale bridge |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
215 |  | Bridges | Structures/ Urban Design & Landscape | Operations | SiD workshop 07/09/23 | User behaviour on Te Awa Kairangi Pedestrian Bridge. | Strong winds, rain reducing usage of the bridge. Anti social behaviour discouraging use of the bridge. | Bridge not used. People falling, getting injured. Increased conflict between cyclists and pedestrians. | Minor | 1 | Almost Certain | 4 | 2 | Medium | Kelsy Seyb/ Nicole Thompson | Provide wind protection in design but ensure this does not encourage the bridge to become a place for anti-social behaviour. CCTV. 04/25 cancel, now not in scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
216 |  | Project Wide | Structures | Natural Disaster | GHD SiD Register - 28 | Additional debris in flood event | Insufficient structural depth at true left bank of the proposed Melling bridge to accommodate services under the deck without creating a debris issue. | Accident / injury | Moderate | 2 | Possible | 2 | 2 | Medium | Kelsy Seyb | Design girders for debris load. 07/25 - current design mitigates this issue as much as possible and GWRC have accepted reduced debris height. | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
217 |  | Bridges | Structures | Natural Disaster | workshop 8/08/23 | Bracket design on bridges | Bracket failure in an earthquake or seismic event | Accident / injury / death to bridge users. Closure of bridge/road(s). | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Avoid fatigue sensitivity 07/25 - designed for fatigue, but nor extreme seismic as this is not part of MR scope. Gantry on SH2 moved to approaches to reduce risk | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
218 |  | Project Wide | Structures | Demolition | SiD workshop 07/09/23 | Fall from height during demolition of structures | Limited planning for unknown conditions associated with deconstructability of damaged structure after earthquake. | Injury/death | Extreme | 4 | Likely | 3 | 4 | Critical | Kelsy Seyb | Aprons in the seating / overlap area at piers/bankseats to allow for robotic wheeled access for remote inspection. Markings on bridge elements to identify where on bridge the inspection drone is viewing for ease of location. Instrumentation - inclinometer, accelerometer, simple telltale elements to show structure deformation / likely loading or damage from a distance 07/25 - design to provide as above, focus on repair in 1st instance, demolition 2ndary |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
219 | Y | Bridges | Structures | Demolition | SiD workshop 07/09/23 | Deconstruction of bridges at end of life. | Complex method involving risky work required to deconstruct bridges. De-construction not considered in design. | Future workers exposed to work at height, over water, live traffic. Injury/accidents. | Severe | 3 | Likely | 3 | 4 | Critical | Kelsy Seyb | Plan how to safely deconstruct the bridges. 07/25 - Modify design where practicable to derisk deconstruction work 06/08/2025 PC - Construction to consider practical approach to removal of elements | Extreme | Unlikely | High | Construction | include in O&M manual |  |  | Unknown |  |  |  | Unknown
220 |  | Project Wide | Utilities | Construction | TAN-0108 | Striking live services during demolition or construction | Unexpected services encountered | Injury / death due to striking live services, damage to services | Extreme | 4 | Almost Certain | 4 | 4 | Critical | Graeme Doherty | Carry out physical service search to help influence design - currently underway. Lots of potholing underway. Redo utilities model. Change design to avoid it. Isolation if possible. Temporary diversions to isolate areas. Requirements of each utility (e.g. strategic assets and standovers). Contractor management plan Registers (e.g. asbestos). 08/25 - design being completed as above, risk transfer to construction team | Extreme | Possible | Critical | Construction | record as-built info accurately |  |  | Unknown |  |  |  | Unknown
221 |  | Project Wide | Utilities | Construction | TAN-0122 | Working with pressure pipe systems for water, stormwater and wastewater (potentially) | Damage to pressurised pipe system | Accident / injury due to pressure release if pipe struck or exposure to contaminated waste within pipes | Severe | 3 | Likely | 3 | 4 | Critical | Graeme Doherty | Design out need to replace these systems. Permit to work LOTO system. Work with asset owners 04/25 - design being completed as above, risk transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
222 |  | Project Wide | Utilities | Construction | TAN-0122 | Wastewater spill during construction | Diversion of existing wastewater lines during construction | Exposure to contaminated waste | Severe | 3 | Possible | 2 | 3 | High | Graeme Doherty | Consideration of diversion / bunging ability during design (can we isolate for long enough). Services location to reduce amount of unknown services. 08/25 - construction risk, transfer to construction team | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
223 |  | Project Wide | Utilities | Construction | workshop 8/08/23 | Overhead powerlines (including Transpower lines) | Construction and O&amp;M equipment/machinery in contact with live overhead power lines. Risk is dependent on temporary works. | Electrocution. Injury, death | Extreme | 4 | Possible | 2 | 4 | Critical | Graeme Doherty | Relocating to underground. Design to avoid conflict - i.e. can we relocate the road to avoid conflict, especially with things that require maintenance Additional signage to identify conflict Attach visibility strips to low hanging powerlines Clash detection using 3d models Surveys of overhead lines to confirm location/ height. Augmented virtual corridors. 08/25 - construction risk, transfer to construction team | Extreme | Possible | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
224 |  | Project Wide | Utilities | Operation | TGDD SiD Register - 117 | Utilities | Damage to utilities due to settlement | Damage to utilities. Injury/accident from gas explosion. Contamination of potable water. Contamination from leaking wastewater. | Severe | 3 | Rare | 0 | 1 | Low | Graeme Doherty | Sufficient clearance to utilities Provide ground improvement to reduce settlement preloading to reduce settlement pipe material - to accommodate expected residual settlement Suitable backfill and bedding Additional support, i.e. support slab/ encasement if required Design to consider construction staging, connections with other utilities. Design so final position is away from possible settlement areas. Expansion joints. 08/25 - design incorporates above wherever practicable, e.g. ground improvements, preloading of fill before ducts installed etc. now a construction risk, transfer to construction team | Severe | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
376 |  | Project Wide | Utilities | Construction/<br>Operation |  | Utilities | Damage to electricity utilities due to settlement | Damage to electricity utilities | Severe | 3 | Likely | 3 | 4 | Critical | Graeme Doherty | Sufficient clearance to utilities Provide ground improvement to reduce settlement preloading to reduce settlement pipe material - to accommodate expected residual settlement Suitable backfill and bedding Additional support, i.e. support slab/ encasement if required Design to consider construction staging, connections with other utilities. Design so final position is away from possible settlement areas. Expansion joints. 08/25 - Duplicate of 223, cancel | Severe | Rare | Low | Cancelled |  |  |  | Unknown |  |  |  | Unknown
225 |  | West Bank | Utilities | Maintenance | TAN-0122 | Wastewater maintenance adjacent to SH2 | Access to utilities, wastewater manholes, valves / flow meters etc. for routine maintenance and inspections within the shoulder of an operational SH2 | Injury / death due to collision with traffic | Extreme | 4 | Possible | 2 | 4 | Critical | Graeme Doherty | Reroute WHSM along river berm. Risk remains at tie in - access manholes not in carriageway. 08/25 - design optimises wherever practicable. transfer to construction team (O&M manual?) | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
226 |  | Project Wide | Utilities | Maintenance | GHD SiD Register - 61 | Leaks in sewer pipeline | Sewer alignment under key features, maintenance requirements | Difficulty maintaining sewer leading to shortened asset life, overflow. | Severe | 3 | Possible | 2 | 3 | High | Graeme Doherty | Access chambers at regular intervals to enable access for relining / CCTV etc. More robust pipe materials where access is limited. Condition assessment of existing sewer and remediation prior to construction of high risk areas. Sewer as shallow as possible. Where possible locate in corridors / areas where excavation won&#39;t have impact on other infrastructure. Stabilisation / protection (e.g. concrete encasement). 08/25 - Duplicate of 222, cancel |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
227 | Y | Project Wide | Utilities | Maintenance | TAN-0122 | Maintenance within confined space/ restricted access | Dry utilities pits/chambers | Injury / death due to being trapped or collision with live traffic | Extreme | 4 | Possible | 2 | 4 | Critical | Graeme Doherty | Remove confined space where possible. Remove need to access chambers / wells (e.g. able to remove equipment / maintain from surface). Retrieval infrastructure (i.e. mounts for davits) Increased access openings and improved ventilation. Controls / double isolation. Ability to open from inside. Adopt maximum depths hat remove risks. Put isolation valves near surface, not 10 m down. 08/25 - design optimises wherever practicable. transfer to construction team (O&M manual?) | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
228 |  | River Works | Rivers | Maintenance | Design Team | Debris clearance |  |  | Extreme | 4 | Possible | 2 | 4 | Critical | Andrew Craig/ Kelsy Seyb | Facilitated with design. Stick to minimum requirements (soffit clearance), maximise bridge spans, minimise piers, consider pier shape. Rip-rap to protect structure where possible to reduce disruptions. Regular inspection and maintenance of temporary works areas. Use CCTV to clear debris before it becomes an issue, e.g. on bridges. Design temporary works to consider flood risk. 04/25 - design optimises wherever practicable. transfer to construction team (O&M manual and/or temp works?) | Extreme | Rare | High | Construction | include operational requirements in O&M manuals |  |  | Unknown |  |  |  | Unknown
306 |  | Project Wide | Stormwater | Natural Disaster |  | Increased rainfall |  |  | Extreme | 4 | Possible | 2 | 4 | Critical | Diana Dumitrascu | 06/25 - design incorporates current rainfall knowledge in accordance with MR's | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
315 |  | Project Wide | General | Operations |  | Risk of local supply chain not being uplifted by the project - start now to train / develop local personnel/businesses in roles where otherwise we're reliant on out-of-region personnel | [6 empty] | No | Unknown |  | 04/25 transfer to constrcution |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
317 |  | Bridges | Structures | Construction |  | Pitching and driving of casing and focal radii |  |  | Moderate | 2 | Likely | 3 | 3 | High | Kelsy Seyb | 07/25 - driving piles from height, design tries to minimise site welding of casings | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
318 |  | Bridges | Structures |  |  | I girder and deck slab handlings - inherent instability | weight, wind, craning and handling | heavy, difficult to handle, high winds | Severe | 3 | Possible | 2 | 3 | High | Kelsy Seyb | 07/25 - construction. weights optimised to allow braced pairs to be installed in stable manner wherever possible. | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
319 |  | Bridges | Structures |  |  | Deck slab temp stability fall between girders | [6 empty] | No | Unknown | Kelsy Seyb | 07/25 - closed, incorporated into 318 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
320 |  | Bridges | Structures | Operation/ Maintenance |  | Confined space access in pedestrian bridge shrouds | [6 empty] | No | Unknown | Kelsy Seyb | 07/25 - removed from scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
321 |  | West Bank | Structures/ Water | Construction |  | Damage to WHMS - New Melling Bridge and city link bridge construction | Installation activity damages the WHMS | Damage to sewer | Moderate | 2 | Unlikely | 1 | 2 | Medium | Keane Kannan | Line pipe to improve structure. Consider in temporary works design. 04/25 - design alignment is as far from bridge as possible, construction risk 06/08/2025 PC - Alignment moved. Coord design through review process as part of construction | Moderate | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
322 |  | West Bank | Structures | De-construction |  | Damage to WHMS - Demo of Old Melling Bridge. | [6 empty] | No | Unknown | Keane Kannan | Protect with temporary works during demolition. 07/25 - construction risk |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
323 |  | Project Wide | Structures | Construction |  | Bentonite spill in river (enviro) | spill or high river | mainly environmental | Moderate | 2 | Possible | 2 | 2 | Medium | Kelsy Seyb | 07/25 - drilling, contamination of acquifer, piling methodology minimises, construction risk | Moderate | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
324 |  | Project Wide | Structures | Construction |  | Temporary support and stability of structures | ground stability | poor ground condition, seismic event | Severe | 3 | Possible | 2 | 3 | High | Kelsy Seyb | 07/25 - design optimises wherever practicable. transfer to construction team | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
325 |  | Bridges | Structures | Construction |  | Services on structure installed on post beam install |  | install/maintain at height, fall | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb/ Graeme Doherty | 07/25 - design optimises wherever practicable. transfer to construction team | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
326 |  | Bridges | Structures | Design | [8 empty] | No | Unknown | Kelsy Seyb/ Graeme Doherty | 04/25 - Design based on having services attached to the beams prior to lifting in. Covered in another SID item |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
327 | Y | Bridges | Utilities | Maintenance |  | Fall from height | Changing street lighting on bridge | Injury | Extreme | 4 | Likely | 3 | 4 | Critical | Graeme Doherty | Access from shoulders either side of bridge. Foldable street lights. LEDS - reduce frequency of maintenance. Elevated platforms. Appropriate training. 08/25 - design ongoing 06/08/2025 PC - Best practice adopted. Access via bucket lift from below. Gantry over shared path will restrict access. Lighting design life 12yr. Ongoing | Extreme | Rare | High | Open |  |  |  | Unknown |  |  |  | Unknown
328 |  | Bridges | Utilities | Maintenance |  | damage to services | Rat problems on bridge | Service disruption | Moderate | 2 | Possible | 2 | 2 | Medium | Graeme Doherty | Spare ducts and pipes. Use galvanised pipes. 08/25 - design incorporates best practice where practicable, e.g. galv pipe to 1m beyond abutments, cap ducts as ducts install etc. Need to review health and safety for maintenance and inspections under bridge for all services and utilities. Sewer rising main has break points in mains so discharge to river, not street. | Moderate | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
329 |  | Bridges | Utilities | Operation, Natural Disaster |  | Lack of separation between/ power and gas in same corridor on bridge. Spark from power igniting leaking gas pipe | leaking/damaged infrastructure, e.g. after a seismic event | Explosion | Extreme | 4 | Likely | 3 | 4 | Critical | Graeme Doherty | 08/25 - design provides for separation where practicable, material choices to minimise risk of damage. Flex joints each end bridge. HDPE, cement lined pipe, pipe stress analysis to be undertaken. Readily accessible to steel pipe, expansion/contraction. | Extreme | Possible | Critical | Open |  |  |  | Unknown |  |  |  | Unknown
330 |  | Project Wide | Utilities | Construction |  | Struck by mobile plant during simultaneous operations. |  | Injury or death | Extreme | 4 | Likely | 3 | 4 | Critical | Graeme Doherty | Permit process - scheduling of utilities activates (programme) 08/25- transfer to construction | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
331 | Y | Project Wide | Utilities | Construction |  | Handover and acceptance of specific work areas. | Lack of comms between stakeholder and divisions. | Disruption to critical path. Re-work. Diminished reputation. | Moderate | 2 | Possible | 2 | 2 | Medium | Graeme Doherty | Pass over of responsibilities document - clearly defined. Sequencing. Constant comms re. programme sequence. 08/25 - transfer to construction |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
332 |  | Project Wide | Utilities | Construction |  | Noise - not being able to hear alarms. | Utilities operators doing work and can't hear because of nearby construction activities. |  | Extreme | 4 | Likely | 3 | 4 | Critical | Graeme Doherty | Permit process - toolbox - multi disciplinary. Sequence of works. 04/25 - transfer to construction | Extreme | Rare | High | Construction |  |  |  | Unknown |  |  |  | Unknown
333 |  | Project Wide | Stormwater | Natural Disaster |  | Flood during inspection | Outlet inspection and flap gate maintenance |  | Extreme | 4 | Likely | 3 | 4 | Critical | Diana Dumitrascu | derisk - provide channels naturalised away from the river. 06/25 - design optimises wherever practicable with outlets located above 15 cumec flood level. | Severe | Possible | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
334 |  | Project Wide | Stormwater | Maintenance |  | Flap gate manual lift space - access to be replaced | insufficient space provided in design | unsafe practices used for maintenance | Moderate | 2 | Possible | 2 | 2 | Medium | Diana Dumitrascu | 06/25 - design makes provision where possible. Vehicle access to be checked | Moderate | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
335 |  | Project Wide | Stormwater | Construction |  | Heavy rain during construction of outlets | [6 empty] | No | Unknown | Diana Dumitrascu | Construct offline. Retain existing during construction. 06/25 - transfer to construction team (O&M manual?) |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
336 |  | Project Wide | Stormwater | Natural Disaster |  | Risk of losing power to penstocks during flood events | loss of power | flooding of local streets | Severe | 3 | Likely | 3 | 4 | Critical | Diana Dumitrascu | Dual - automated and manual 06/25 - design optimises wherever practicable. Look into sensors for flap gate to show if they are open/closed. Design includes provision for manual override, generator connection, battery back up. | Severe | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
337 | Y | Project Wide | Stormwater | Maintenance |  | Safe access for maintenance parking space everywhere | [6 empty] | No | Unknown | Diana Dumitrascu | 06/25 - covered under other SID item |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
338 | Y | Project Wide | Stormwater | Maintenance |  | MH lids in the cycleway | [6 empty] | No | Unknown | Diana Dumitrascu | 06/25 - covered under other SID item |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
339 |  | Project Wide | Water | Natural Disaster |  | Water ring main | Seismic event | Replacement Fixing of pipe | Moderate | 2 | Likely | 3 | 3 | High | Keane Kannan | consider HPDE - easier to pull (through sleeves) during construction 06/25 - on going safety risk review as design progresses | Moderate | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
340 |  | West Bank | Sewer | Construction |  | WHMS Manhole construction | Complex/deep construction in-situ (3m Dia) | Injury |  |  |  |  | No | Unknown | Keane Kannan | Modularise construction 06/25 - construction risk |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
341 |  | West Bank | Sewer | Construction |  | Extent of WHMS construction | Work within active river | [5 empty] | No | Unknown | Keane Kannan | CIPP lining - reduce extent 06/25 - design optimises wherever practicable. transfer to construction team |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
342 |  | Project Wide | Water | Construction |  | Run to waste - safety of people working at outlet or working on new pipe | 100l/s exits at any time bores are changed. | injury | Severe | 3 | Possible | 2 | 3 | High | Keane Kannan | Keep people clear of outlet and coordinate work with Wellington Water. 06/25 - on going safety risk review as design progresses | Moderate | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
343 |  | River Works | River | Construction |  | Stockpiling of material in the river corridor | increased sediment mobilisation. | [5 empty] | No | Unknown | Andrew Craig | Flood response plan. Installing temporary barriers to stabilise Use low tox materials. 04/25 - transfer to construction team |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
344 |  | River Works | River | Design |  |  | Increased flood. | [5 empty] | No | Unknown | Andrew Craig | Hydraulic monitoring Toe bunding. Locating area in low velocity sediment. |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
345 |  | East Bank | River | Natural Disaster |  | Outlet 40 temporary flood protection | [6 empty] | No | Unknown |  | what line is selected and barriers on top of stopbank as a temporary measure. 04/25 - now excluded from alliance scope |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
346 |  | Project Wide | Utilities |  |  | tracking services located parallel to the stopbank. |  |  | Extreme | 4 | Unlikely | 1 | 3 | High | Graeme Doherty | Move services away from stopbanks where possible. 08/25 - minor works only as predominately excluded from alliance scope | Extreme | Rare | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
347 |  | West Bank | River | Operation |  | WHSM scour protection | Flood event | damage to infrastructure, challenging to repair | Moderate | 2 | Likely | 3 | 3 | High | Andrew Craig/ Keane Kannan | Design flood/scour protection. Collaboration between Alliance and GW. Type of pipe to design to. 04/25 - design & discussions ongoing | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
348 |  | Bridges | Urban Design & Landscape | Operation |  | Passive surveillance with bridges | [6 empty] | No | Unknown | Nicole Thompson | 04/25 - covered under 071 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
349 |  | Bridges | Urban Design & Landscape | Operation |  | Cycle stair conflict - pedestrian bridge ends | [6 empty] | No | Unknown | Nicole Thompson | 04/25 - cancel, covered under another item |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
350 |  | Bridges | Urban Design & Landscape | Operation |  | Fishing from ped bridge? | [6 empty] | No | Unknown | Nicole Thompson | now excluded from scope of work |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
351 |  | Project Wide | Traffic & Transport | Construction |  | Logistics around temporary bus stops. Moving people to Western Hutt/Petone | [6 empty] | No | Unknown | Mike Pilgrim | 04/25 liaise with bus operators, TMP to include |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
352 |  | Project Wide | Urban Design & Landscape | Construction |  | Construction Public access | [6 empty] | No | Unknown | Matt Fairweather | 04/25 - construction risk |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
353 |  | West Bank | Urban Design & Landscape |  |  | Share footpath south station not pink | inconsistent marking | confused pedestrians and motorists | Moderate | 2 | Possible | 2 | 2 | Medium | Nicole Thompson | not proposed to be part of design 04/25 - TBC | Insignificant | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
354 |  | West Bank | Urban Design & Landscape |  |  | TRB carpark and rail and SH2 access - fence and planting |  |  | Severe | 3 | Possible | 2 | 3 | High | Nicole Thompson | Designed out |  |  | Unknown | Closed |  |  |  | Unknown |  |  |  | Unknown
355 | Y | West Bank | Urban Design & Landscape | Operation |  | Turning into Melling Line | sight distances obstructed | pedestrian hit by vehicle | Moderate | 2 | Possible | 2 | 2 | Medium | Nicole Thompson | adopt landscaping features that will provide appropriate sight distances 06/25 - HCC, issue no longer relevant, cancel | Moderate | Rare | Low | Cancelled |  |  |  | Unknown |  |  |  | Unknown
356 | Y | West Bank | Geometrics | Operation |  | Cyclists and cars shared along Casa Loma |  |  | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim/ Steve Muller | 04/25 - best practice design adopted 06/08/2025 PC - See above. Ongoing | Severe | Possible | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
357 | Y | Project Wide | Geometrics | Operation |  | No tables at local road intersections | not in design | cost, council not accepting etc | Severe | 3 | Likely | 3 | 4 | Critical | Mike Pilgrim | 04/25 speed management measures incorporated into design, ongoing | Moderate | Possible | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
358 |  | West Bank | Rail | Construction |  | Line Closure Design Works/Timing and implementation | Delay in completing requirements for closure, design etc | Delay to programme, construction constraints, access safety | Severe | 3 | Likely | 3 | 4 | Critical | Blair Rogers | Communication and coordination of critical milestones to achieve closure date. 06/25 - cancel, repeat of item above | Severe | Possible | High | Cancelled |  |  |  | Unknown |  |  |  | Unknown
359 |  | West Bank | Rail/ Active Modes | Operation |  | Shared Path cycleway manhole lid hazard | manholes in the middle of the pathway, slippery surface. | Accident to cyclists | Severe | 3 | Likely | 3 | 4 | Critical | Blair Rogers | Design manhole lids offset to centre. Review lid material for slip resistance. 06/25 manholes positioned to minimise likelihood of cyclists | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
360 |  | West Bank | Rail | Operation |  | Emergency access along rail corridor | Train breakdown requires passengers to walk along the rail corridor | Slips, trips or falls | Severe | 3 | Possible | 2 | 3 | High | Blair Rogers | For reduced width areas flatten ballast edge against robust wall for access. 06/25 - cancel, repeat of above item | Severe | Unlikely | Medium | Cancelled |  |  |  | Unknown |  |  |  | Unknown
361 | Y | Project Wide | General | Construction |  | Noise/vibration impacts on surrounding residences and businesses. Potential structural damage to surrounding buildings. | Vibration from construction machinery. | damage to adjacent infrastructure, buildings, houses etc. | Severe | 3 | Likely | 3 | 4 | Critical | Matt Fairweather | 04/25 design incorporates design elements where possible to reduce vibration. transfer to construction | Severe | Likely | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
362 | Y | Project Wide | General | Maintenance |  | Substantial detour routes during maintenance works | roads not previously subjected to detour traffic volumes and loading | damage to roads etc, unsafe driving, increased interface between vulnerable road users and increased traffic | Extreme | 4 | Likely | 3 | 4 | Critical | Mike Pilgrim | 04/25 design incorporates design elements where possible. TMP/construction to take into consideration | Extreme | Likely | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
363 | Y | Project Wide | Utilities | Construction |  | Electrical clearance from distribution networks | insufficient space | interference | Severe | 3 | Possible | 2 | 3 | High | Graeme Doherty/ Matt Fairweather | 08/25 - separation provided in design to all known services. unknown services to be managed during construction, transfer to construction | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
364 |  | West Bank | Rail | Construction |  | Clearance from rail operations | [6 empty] | No | Unknown | Blair Rogers | 06/25 included in other items, cancel |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
365 |  | West Bank | Geotechnical | Construction |  | Slope collapse north side of SH2 | [6 empty] | No | Unknown | Russell Allison | 04/25 Repetition of other SID items |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
366 |  | West Bank | Stormwater | Maintenance |  | Flooding/flood debris effecting road/rail - crossing from north side of SH2 (existing issue) | Flood event | crossing cannot be used | Moderate | 2 | Likely | 3 | 3 | High | Diana Dumitrascu | 06/25 - design minimises risk as much as practicable. looking at fences and debris traps to minimise debris flow upstream of pipework. Some existing dams and ponds already exist. O&M manual 06/08/2025 PC - Flooding could encroach on SH in extreme event. Ongoing maintenance requirement | Moderate | Possible | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
011b |  | Project Wide | General | Construction | GHD SiD Register - 59 | Contact with contaminated land | Contact with contaminated material - e.g. asbestos during building demolition, unknown material within stopbanks, works in HAIL sites, rail corridor, relocation of train station building | Illness / death | Extreme | 4 | Possible | 2 | 4 | Critical |  | Use available technical report #13 and GWRC SLUR register to minimise design elements &amp; change of ground level in medium/high risk areas where possible. Utilise gas monitors and masks whenever contamination concern is identified. Test all building materials that have the potential to contain asbestos to allow early identification. 15/04/25 - contamination identified in rail ballast, design options being considered, constrcution risk. see 011a | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
367 |  | Project Wide | Utilities | Construction/ Operation |  | Striking live services during demolition or construction | Failure to incorrectly identify services | Loss of services |  |  |  |  | No | Unknown | Graeme Doherty/ Matt Fairweather | Relocating telecommunication services clear of the construction site prior to starting. 08/25 - duplicate of 222, cancel |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
368 |  | West Bank | Rail | Construction |  | NEW - Limits of Permit to Enter requirements not clearly defined - Breach in regulator requirements. | Construction personnel and contractors not aware of Permit to enter requirements (including medicals for all staff) | [5 empty] | No | Unknown | Blair Rogers/ Matt Fairweather | 06/25 transfer to constrcution |  |  | Unknown | Construction |  |  |  | Unknown |  |  |  | Unknown
369 |  | West Bank | Stormwater | Design |  | Track drainage insufficient reducing asset life due to drains not sufficient | poor drainage | asset life reduced, premature failure of asset | Moderate | 2 | Almost Certain | 4 | 3 | High | Diana Dumitrascu | 06/25 - best practice drainage design being adopted. change discipline to stormwater 06/08/2025 PC - N/A Rail activity | Moderate | Rare | Low | Cancelled |  |  |  | Unknown |  |  |  | Unknown
370 |  | West Bank | Stormwater | Operation |  | Existing SH2 flooding issue (between Normandale bridge and Melling intersection) transferred onto rail alignment / or leading to blockage of drainage | poor drainage | increased risk to rail | Severe | 3 | Possible | 2 | 3 | High | Diana Dumitrascu | 06/25 - best practice drainage design being adopted. change discipline to stormwater 06/08/2025 PC - Drainage developed. Ongoing | Severe | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
371 |  | West Bank | Geometrics | Operation |  | Vehicle collision on motorway ejecting vehicle onto rail corridor (in front of passenger service or entaglement on OHLE wire) | insufficient barrier or barrier deflection | electrocution and/or vehicle/train interaction | Extreme | 4 | Possible | 2 | 4 | Critical | Steve Muller | 04/25 - best practice design in accordance with MR's applied 06/08/2025 PC - Existing risk to be managed. Ongoing | Extreme | Unlikely | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
372 |  | West Bank | Rail | Design |  | Timber OHLE structures (currently supporting 3rd party FOC) need to be removed - legacy hazard to rail corridor |  |  | Moderate | 2 | Possible | 2 | 2 | Medium | Blair Rogers | 06/25 all redundant will be removed. 3rd part fibre optic cabled transferred to underground duct(s) | Insignificant | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
373 | Y | West Bank | General | Construction |  | Pharazyn street is important throughfare for HV traffic between southbound motorway and Gracefield industrial area - Traffic issues if obstructed by construction works | blocked or restricted access to street | Moves traffic to adjacent streets, damage to roads etc, unsafe driving, increased interface between vulnerable road users and increased traffic | Extreme | 4 | Likely | 3 | 4 | Critical | Matt Fairweather | 04/25 transfer to constrcution | Extreme | Likely | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
374 |  | Project Wide | Stormwater | Natural Disaster |  | Increased rainfall | [6 empty] | No | Unknown | Diana Dumitrascu | CC implemented everywhere. Medium - high range - Rep 6 04/25 - duplicate of 306 |  |  | Unknown | Cancelled |  |  |  | Unknown |  |  |  | Unknown
375 |  | Project Wide | ITS/Lighting/CCTV | Operation |  | EV charging - vehicles / motorbike / ebike stations - potential hazard with floodwater ? | Hazard with flood water | electrocution | Extreme | 4 | Possible | 2 | 4 | Critical | Daniel Lovisa/ Mike Pilgrim | 04/25 - design incorporates best practice | Extreme | Unlikely | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
376 | Y | Project Wide | Stormwater | Design |  | Pavement drainage considerations - remove maintenance locations from traffiked areas (*eg motorway median drainage / trackside drainage | safety risk for maintenance activities |  | Severe | 3 | Likely | 3 | 4 | Critical | Diana Dumitrascu | 06/25 - maintenance requirements within trafficked areas minimised / optimised where possible. Need to consider access requirements without compromising road user safety WIP 06/08/2025 PC - Reduced drainage accessible infrastructure as part of design. Ongoing | Severe | Possible | High | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
377 |  | Project Wide | Geometrics | Design | 30% dsign review | Cyclist crash risk (as riders drift into the path of oncoming riders). | Consider how the camber/crossfall of the cycleway may present a negative camber/crossfall at the point where the path turns into/away from the rail corridor. Combined with a very tight radius of turn | cyclist fall | Moderate | 2 | Possible | 2 | 2 | Medium | Diana Dumitrascu | 15/04/25 The crossfall and kerb setout at the start of the project is the same as the recently completed Petone to Mellng (P2M) cycleway, so no transition is needed. The P2M layout leads from the shared Parliament Street roadway/cycleway to the new cycleway, there should be no issues for tight radius turns. There will need to be a central folding bollard installed so that vehicles cannot access the cycleway unless for maintenance. At the northern end of the cycleway the intent is for the cross fall to change from falling towards the rail corridor, to falling towards the inside of the curve. Grades will be determined during the next design phase 04/25 - as above 06/08/2025 PC - Design to incorporate line marking requirements. Bollards are N/A | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
378 |  | Project Wide | Stormwater | Design, operation | 08/07/2025 SID workshop | cycle wheels falling between cycle grates, slippery manhole lids, locations in shared paths and cycleways. High shoulder to edge detail can facilitate the ponding of water ponding, which can impact cyclists movements and safety in the shoulder | gaps in grate etc | injury | Severe | 3 | Likely | 3 | 4 | Critical | Diana Dumitrascu | 06/25 - Cycle friendly sump grates, anti slip manhole cover surfacing, locate outside shared paths and cycleways where possible 06/08/2025 PC - Design as MRs. Ongoing | Moderate | Unlikely | Medium | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
390 |  | East Bank | Water | operation | 08/07/2025 SID workshop | Liquefaction | earthquake | infrastructure floats/lifts | Severe | 3 | Likely | 3 | 4 | Critical | Anna Liu | 06/25 - liquefaction assessment to be completed, recommendations agreed and incorporated into design | Severe | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
381 |  | River Works | Stormwater | Construction | 08/07/2025 SID workshop | deep excavation, break in continuous layer construction of flood bank |  | weak point in flood bank | Moderate | 2 | Likely | 3 | 3 | High | Diana Dumitrascu | 06/25 - Look at design options to remove redundant assets through flood bank without need to excavate through new stop bank | Moderate | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
379 |  | Project Wide | Stormwater | Design, operation | 08/07/2025 SID workshop | manhole and sump maintenance may require maintenance vehicles to block shared path(s) | sumps and manholes in shared paths | diversion of cyclists and pedestrians to less safe routes | Severe | 3 | Likely | 3 | 4 | Critical | Diana Dumitrascu | 06/25 - Specific temporary traffic measures to be developed and implemented. Transfer to construction and O&M manuals | Severe | Unlikely | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
380 |  | River Works | Stormwater | construction | 08/07/2025 SID workshop | Working in river corridor during construction, maintain LOS for flood protection during construction. Interface between GWRC and alliance work. Design to allow for where practicable. River can get up to 8m deep | flooding, in particular flow to local streets etc due to construction not proving LOS during construction | flooding outside of stop banks | Severe | 3 | Likely | 3 | 4 | Critical | Diana Dumitrascu | 06/25 - Ensure design incorporates measures to allow construction to be undertaken without compromising stop bank LOS | Severe | Unlikely | Medium | Open |  |  |  | Unknown |  |  |  | Unknown
383 |  | East Bank | Water | design, maintenance | 08/07/2025 SID workshop | ac pipe being abandoned. | n/a | Potential for asbestos contact in future if not removed | Extreme | 4 | Possible | 2 | 4 | Critical | Anna Liu | 06/25 - Is abandoned AC pipe being removed up to 1m deep with deeper areas retained and grouted? If any lengths retained, will they be an issue? Ideal is to remove if possible, otherwise grout. Check MR's | Extreme | Possible | Critical | Open |  |  |  | Unknown |  |  |  | Unknown
385 |  | East Bank | Water | design, maintenance | 08/07/2025 SID workshop | accessibility to and within deep manholes etc. |  | confined space | Extreme | 4 | Possible | 2 | 4 | Critical | Anna Liu | 06/25 - Wellington Water design requirements being applied. Need for landing in manhole, safety grill under lid (>3m), tripod area to lower people into MH's etc. Able to remove flapgates etc, special lids, McBerns safety lid. O and M manual. Area to park close by, not in traffic lane etc. | Extreme | Rare | High | Open |  |  |  | Unknown |  |  |  | Unknown
382 |  | River Works | Stormwater | maintenance | 08/07/2025 SID workshop | difficult access to outfalls may result in scour repair etc. not being completed | poor access | repairs not completed | Severe | 3 | Possible | 2 | 3 | High | Diana Dumitrascu | 06/25 - no known issues, but TBC, especially that GWRC and Alliance designs align | Severe | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
386 |  | East Bank | Water | operation | 08/07/2025 SID workshop | Access to deep valves and hydrants | deep valves and hydrants | inaccessible | Moderate | 2 | Possible | 2 | 2 | Medium | Anna Liu | 06/25 - valve spindles extended and hydrant risers raised | Minor | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
384 |  | East Bank | Water | design, construction | 08/07/2025 SID workshop | infrastructure removal may result in reduced LOS if not completed post operational of new assets. e.g. hydrants |  | reduced fire fighting capacity, services unaware of new infrastructure locations | Extreme | 4 | Possible | 2 | 4 | Critical | Anna Liu | 06/25 - ensure construction team removes redundant infrastructure only when new is operational. Advise locations of new infrastructure to all relevant parties | Severe | Rare | Low | Construction |  |  |  | Unknown |  |  |  | Unknown
388 |  | East Bank | Water | design | 08/07/2025 SID workshop | access to air valves, protection provided for the public and infrastructure | inadequate protection, poor location | damage, harm to public | Moderate | 2 | Possible | 2 | 2 | Medium | Anna Liu | 06/25 - design to be reviewed | Moderate | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
387 |  | East Bank | Water | design | 08/07/2025 SID workshop | flood or seismic event disables power supply to valves | extreme event(s) | unable to operate | Severe | 3 | Possible | 2 | 3 | High | Anna Liu | 06/25 - power supply set above flood level, designed for seismic loads | Severe | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
195b |  | Bridges | Structures | Construction | SiD workshop 07/09/23 | Tight confined spaces producing challenges for steel fixing and bearing installation | Insufficient space for complex rebar and built in items | Injury to steel fixers or carpenters. Quality issues | Extreme | 4 | Possible | 2 | 4 | Critical | Kelsy Seyb | Prefabricate. Use alternatives to reinforcement. Post-tensioning. 07/25 will be looked at more as design progresses including reinforcement detailing, post tension design, etc. construction risk also | Severe | Unlikely | Medium | Construction | Prefabricate |  |  | Unknown |  |  |  | Unknown
389 |  | East Bank | Water | operation | 08/07/2025 SID workshop | Gas build up in sewer | inadequate ventilation | gas explosion | Extreme | 4 | Possible | 2 | 4 | Critical | Anna Liu | 06/25 - best practice design to Wellington Water standards applied. use gas detectors | Extreme | Rare | High | Open - Specified |  |  |  | Unknown |  |  |  | Unknown
391 |  | East Bank | Water | Sewer WHMS-2 inaccessible | 08/07/2025 SID workshop | inaccessible | deep sewer, limited access | difficult to maintain and to clear if blocked | Moderate | 2 | Possible | 2 | 2 | Medium | Anna Liu | 06/25 - Access to be reviewed | Moderate | Rare | Low | Open |  |  |  | Unknown |  |  |  | Unknown
071b | Y | Project Wide | Urban Design & Landscape | Operation | workshop 8/08/23 | CPTED measures do not deter criminals Movement restrictions in locations where crime is increased due to low level of lighting and CCTV e.g. narrow spaces under bridges. | Unsafe user behaviour. People loitering in carpark if carpark is visually recessive space. Movement restrictions in locations where crime is increased due to low level of lighting and CCTV e.g. narrow spaces under bridges. Safety risk for homeless/criminal activity under the bridge or either side of the stopbank. | Harm to person or damage / vandalism to assets. Injury or death | Extreme | 4 | Possible | 2 | 4 | Critical | Nicole Thompson | Bridge form selection to deter access. Provision of alternative desirable areas. CCTV presence. Lighting design extent and specifications. Removal of high walls, dead ends. Low planting. 10/04/25 consider as part of TMP | Extreme | Unlikely | High | Construction |  |  |  | Unknown |  |  |  | Unknown
|  | West Bank | Rail | Operational |  | Hi rail access locations | Hi-Rail location near the station platform and also the exit of the cycleway to Pharazyn Street, Conflict with pedestrians/cyclists for the Hi-Rail access | Hi Rail too close to the station/cycle storage and the cycleway exit point | Moderate | 2 | Likely | 3 | 3 | High | Blair Rogers | 06/25 Hi-Rail design has been located with sufficient clearance to both the station and the cycleway exiting, 50m+ with visibility for both directions. Sliding cantilevered gates added to mitigate opening and additional visibility hazards | Moderate | Rare | Low | Open - Managed |  |  |  | Unknown |  |  |  | Unknown
[13 empty] | No | Unknown |  |  |  |  | Unknown |  |  |  |  | Unknown |  |  |  | Unknown
392 | Y | East Bank | General | Operation | HCC SID workshop 25/06/2025 | Local roads redesignated as OD route | Existing culverts, bridges, and underground infrastructure are failing or collapsing, as they may not have been designed to withstand the imposed loading. | damage to infrastructure, unsafe driving, increased interface between vulnerable road users and increased traffic | Severe | 3 | Possible | 2 | 3 | High |  | 06/25 - Design incorporates safety mitigation where practicable. Transfer to construction to take into consideration with TMP's etc | Moderate | Possible | Medium | Construction |  |  |  | Unknown |  |  |  | Unknown
393 | Y | Project Wide | General | Construction | HCC SID workshop 25/06/2025 | Disruption to emergency services including police, fire, hospital access for patients, emergency services, and staff due to construction activities. | Road closures, diversions, reduced parking, increased congestion, and confusion from changing access routes, particularly impacting vulnerable groups such as the elderly, disabled, and those unfamiliar with the area. | Construction works may impact access routes to nearby hospitals, affecting both pedestrian and vehicle movements. This poses a risk of delayed access for emergency services (ambulances, fire, police), patients attending urgent appointments, and hospital staff, potentially leading to serious health and safety consequences. | Extreme | 4 | Possible | 2 | 4 | Critical |  | 06/25 - Design incorporates safety mitigation where practicable. Transfer to construction to take into consideration with TMP's etc | Extreme | Possible | Critical | Construction |  |  |  | Unknown |  |  |  | Unknown
394 | Y | Project Wide | General | Construction | HCC SID workshop 25/06/2025 | Outdated or incorrect navigation information (e.g., Google Maps, GPS apps) | Disruption to wayfinding due to Google Maps and other navigation apps not being updated with construction-related road closures or detours. | This may lead drivers, including emergency services, patients, and hospital staff, to follow incorrect routes, potentially directing them through closed roads or restricted areas, increasing the risk of delays, confusion, and unsafe vehicle movements. | Severe | 3 | Possible | 2 | 3 | High |  | 06/25 - Design incorporates safety mitigation where practicable. Transfer to construction to take into consideration with TMP's etc. | Severe | Possible | High | Construction |  |  |  | Unknown |  |  |  | Unknown
[13 empty] | No | Unknown |  |  |  |  | Unknown |  |  |  |  | Unknown |  |  |  | Unknown
[13 empty] | No | Unknown |  |  |  |  | Unknown |  |  |  |  | Unknown |  |  |  | Unknown
[13 empty] | No | Unknown |  |  |  |  | Unknown |  |  |  |  | Unknown |  |  |  | Unknown
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Still critical?
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ?
Note on H244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ?