## Sheet1
August 2016 Stocktake of Taupo Fishery Review Implementation Plan/doc 2839410
|  | Lead | Support | Advise
Opportunities | Implementation Time Frames (S,M,L,O) | Priority (1,2,3) | Level (Gov, Mgmt, Ops) | Resources Services | Resources Community rangers | Resources Admin | Resources Legal | Resources NO | Resources TMTB | Resources TFAC | Timeframes | Notes | Review date | Outcomes
A1. Establish a clear goal for the management of the Taupō Fishery that focuses on maximising the full value (in economic, environmental, social and cultural terms) that the Fishery can deliver. | L | 1 | Gov & Mgmt | ü | ü |  |  |  | ü | ü | Ongoing | Michel Dedual is currently working on a strategy document which will inform this process, drawing on his experience at the World Recreational Fishing Conference. This will be presented at TFAC for discussion before moving into management planning.2nd Draft stage Will be completed as part of the renewal of the Taupo Fishery management plan. Intended to begin 2016/17 season | 2016-12-01
E1 (a). Put in place an on-line system in close collaboration with Fish and Game; | S | 1 | Mgmt | ü | ü | ü | ü | ü |  |  | Completed | System upgrades are on-going, including NZ Post address finder for 2016 season. This is currently in the testing phase for delivery September 2016 | 2016-09-01
C1 Work with Ngāti Tūwharetoa and licence-holders either to refine or develop new management structures and processes for the management of the Taupō Fishery | S | 1 | Mgmt | ü | ü |  |  |  | ü |  | Completed | Completed with new structure in place. Realignment in February 2016 of DOC has settled our management structure, very flat structure now in place with one accountable manager. |  | Complete
D6. Initiate the planned review of the entire Tongariro National Trout Centre site and examine the role of the hatchery in that wider context | S | 1 | Mgmt | ü | ü |  | ü |  | ü |  | Completed | Review completed by external contractor. We have moved into first recommendation, to set up the transitional Governance Group to prepare the Trout centre site for the post treaty settlement landscape. |  | Complete
C4. Re-examine existing administrative and overhead charges and identify where savings can be made and applied to the operational management of the Taupō Fishery. | O | 1 | Mgmt | ü |  | ü |  |  |  |  | Ongoing with a continued review during annual business planning | There have been some significant savings achieved in a number of areas with obvious examples being the production and distribution methods of Target Taupo, the online licence purchase portal, the introduction of plastic cards and electronic distribution of licences. Administration savings are considered during business planning also. | Feb 2017 Business planning
E4 (a). Develop a new communications strategy, including reconsidering the role of the Target Taupō publication; | S | 1 | Mgmt | ü | ü | [5 empty] | Ongoing | Social media and facebook strategies complete and being implemented. Next step is to review the widers coms strategy for the fishery. In the meantime TT will continue, next issue planned for Oct 2016 | Feb 2017 Business planning
E4 (c). Review the Department’s website and explore the benefits of a standalone Taupō Fishery website; and | S | 1 | Mgmt | ü | ü |  |  |  | ü |  | Completed | Stand alone website cannot be achieved, Fishery must remain under current DOC structure. National Office has made moves to promote the visibility of the fishery licencing system, but the fishery web pages remain under the umbrella of the wider department. |  | Complete
B2. Agree on processes that give better effect to the existing shared decision making (concurrence) role in relation to fixing of forms and classes of fishing licenses and fees for licenses; | Ongoing | 1 | Mgmt | ü |  |  |  |  | ü |  | Ongoing | Work underway to prepare paper for licence increase for 2017/18 to TMTB. Agenda item for TFAC in September, with feedback due pre christmas. Concurrence process via Forms, Fees and Letters process to be underway early 2017 in time for the 2017/18 season. | 2016-10-01
B3 Develop stronger links between Ngāti Tūwharetoa governance and statutory decision-making roles, and their role in the current, and any future, management structures. | O | 1 | Mgmt | ü |  |  |  |  | ü |  |  | Refer C1.
E4 (b). Adopt regular, timely and less formal communication, including better use of social media and more active engagement with and support for existing sites; | O | 1 | Mgmt/Ops | ü | ü |  |  |  | ü |  | Ongoing | Fishery Facebook & website is being maintained. Limited capacity for regular weekly media, but will improve once Community ranger finishes her secondment. | Monthly comms meeting
F 1, Promote stronger alignment with Fish and Game, including, where appropriate, shared strategy, research and infrastructure, shared processes, and more consistent regulations | O | 1 | Mgmt | ü | ü | [5 empty] | On-going | In particular Michel Dedual is working closely with Fish and Game on several projects. Close liaison with F&G re TFAC and Licence categories. Currently involved with the lake Rotoiti catfish incursion, and also in discussions re sharing knowledge and software for smelt monitoring in Lake Te Anau.
C3 Work with the Taupō Fishery Advisory Committee in the short-term to ensure it is supported to provide an effective angler voice in the management of the Taupō Fishery | O | 1 | Mgmt/Gov | ü | ü |  |  |  | ü | ü | On-going | Work is ongoing to have better engagement and involvement with TFAC in Fishery planning and regulatory processes. Current examples are the licence fee setting and category discussions which are on the agenda for September. | 2016-10-01
Opportunities | Implementation Time Frames (S,M,L,O) | Priority (1,2,3) | Level (Gov, Mgmt, Ops) | Resources Services | Resources Community rangers | Resources Admin | Resources Legal | Resources NO | Resources TMTB | Resources TFAC | Timeframes | Notes
E1 (e). More actively promote the fact that licence fees pay for fishery management + rights to access | O | 1 | Mgmt/Ops | ü | ü | [5 empty] | Ongoing, | utilising Target Taupo primarily as our long form media.Upcoming example is the licence sales report in the next issue of Target taupo | Monthly comms meeting
D3 (a)(b). Establish clear processes to ensure that science and monitoring information is used effectively to: | O | 2 | Mgmt/Ops | ü | [5 empty] | ü | Ongoing, | will be more visible now that Angler Notices are in effect, allowing for more speedy changes to fishing methods etcAs part of the process of developing the 2017/18 Angler Notice our science and research will be vital in determining likely changes to current bag limits. Agenda item for upcoming TFAC meeting. | 2016-10-01
a. Take a more active role in ‘intervening’ in the Fishery; | [11 empty] | Contribution from TFAC required re: Anglers
b. Monitor the effectiveness of those interventions; and communicating with anglers | [6 empty] | ü
B1 Establish a shared decision-making role for Ngāti Tūwharetoa for approving the sports fish management plan through a legislative change, and/or establish agreed engagement processes for the preparation and approval of the sports fish management plan | S-Medium | 2 | Gov | ü | ü |  | ü | ü | ü |  | On hold. | Will be progressed prior to the management plan process coming to a close. | 2016-02-01
D5. Consider initiating a pilot programme to reduce the number of catfish in Lake Taupō | S-M | 2 | Mgmt/Ops | ü | ü |  |  |  | ü |  | Research completed | TMTB successful in funding koura/catfish research. Impacts on Koura assessed, possibility that TMTB could explore catfish suppression based on this report. MPI have the legal responsibility to manage this issue, but DOC fishery is prepared to provide expertise and support for any initiative in the event. | Complete, not the role of DOC fishery to progress this, but prepared to support initiatives led by MMPI or TMTB
A2 Align the management of the Taupō Fishery to the new goal by: a. Setting meaningful management objectives and targets; b. Aligning the staffing structure and budget allocations; and c. Monitoring and reporting progress against the objectives and targets. | S - M | 2 | Mgmt | ü |  |  |  |  | ü |  | Ongoing | Delivery of this goal is dependant on the delivery of A1 above
E1 (c). Offer a fuller range of licence options, with the priority being a family licence, a weekend licence, and a 12 month licence; | M | 2 | Mgmt/Gov | ü | ü |  | ü |  | ü | ü | Commenced | Planning underway to undertake a Form, fees and letters process this year (2016/17) to feed in to the concurrence process with TMTBProposal to be prepared for TMTB. Will engage with Fish and Game, given their recent implementation of a wide range of licences. Will also have heavy input from TFAC. Is an agenda Item for TFAC meeting September, with report back due pre christmas.Annualised (12 month) licence is unlikely to be achieved due to current government financial practices. | 2016-12-01
E1 (d). Consider ways to support charter boat operators in the development of a boat licence concept; and | M | 2 | Mgmt/Gov | ü | ü |  | ü |  | ü | ü | Ongoing | We have implemented the required changes to the Taupo Fishery Regulations 2004 which were needed to make this possible. Next steps are to engage DOC expertise in the field of permissions in order to develop an appropriate charging regime. | 2017-02-01
E3 (a). Expand opportunities to learn to fish for all people, including expanding the kids ‘fish-out’ days to a daily occurrence for all visitors (not just children); | M | 2 | Mgmt |  | ü |  |  |  | ü |  | Ongoing | Trout centre Society very active in increasing opportunity, particularly during peak holiday periods. | Review on case by case basis
E3 (c). Work with others to develop a policy-driven approach to enabling more spin fishing opportunities in the Fishery. | M | 2 | Mgmt/Gov/Ops | ü | ü |  | ü | ü | ü | ü | Ongoing | Will be one of the items to be progressed now that Angler Notices have been implemented. TFAC will be integral in moving forward with this issue as it will be highly contentious based on experience of F&G | 2017-02-01
E4 (d). Develop clear financial reporting for licence-holders. | M | 2 | Mgmt | ü | ü | [5 empty] | Ongoing, | Through newsletter, Target Taupo and TFAC. Target due for publishing late October 2016 and will have brief financial report.
Opportunities | Implementation Time Frames (S,M,L,O) | Priority (1,2,3) | Level (Gov, Mgmt, Ops) | Resources Services | Resources Part | Resources Admin | Resources Legal | Resources NO | Resources TMTB | Resources TFAC | Timeframes | Notes
E2 (b). Develop and implement a marketing and communications plan to raise the profile of the fishery nationally and internationally; and | M | 2 | Mgmt |  | ü | [5 empty] | On hold, | awaiting the completion of the taupo Fishery management plan. See F2 below also
D4. Amend the current Taupō Fishery Regulations to enable the use of Angler Notices as the key mechanism for regulating angler impacts on the Fishery | M-L | 2 | Mgmt | ü |  |  | ü | ü |  |  | Completed | First angler notice published 27 May 2016
F2. Work collaboratively with Destination Great Lake Taupō and the wider tourism and commercial sector to explore more innovative ways of working together to promote and market the Taupō Fishery and the wider region | M-L | 2 | Mgmt |  | ü | [5 empty] | Commenced, | currently working with DGLT to run a spring 2016 campaign to help drive increased short stay angler visits to TurangiLatest meeting August 15, agreed to take part in small campaign over spring, DOC acknowledges that DGLT holds the relevant expertise in marketing the region and the fishery, as it is not core delivery work for us. DOC is very willing to support DGLT in delivering this campaign and reviewing the outcomes. | 2016-09-01
F3. Support the Lake Rotoaira Trust (LRT) in developing its vision for Lake Rotoaira. | M-L | 2 | Mgmt/Ops | ü | ü |  |  |  | ü | ü | Commenced | Dave working with DOC Treaty team & LRT to assist with facilitating their aspirations. | Awaiting LRT
D8. Investigate the use of infringement notices for minor breaches of fishing regulations. | Long | 3 | Mgmt |  |  |  | ü | ü |  |  | Commenced | Progressing through the legislative drafting process currently. Hopeful that implementation will occur late 2017. | Not locally led, contingent on DOC legal and the legislative process
E2 (c). Initiate the development of a collective vision and a strategic plan for the Tongariro River to address the competing demands on the river and surrounding land. | L | 3 | Mgmt |  | ü | [5 empty] | On hold | Awaiting settlement of the Ngati Tuwharetoa Collective Claim under the Treaty of Waitangi
C2 Consider the development of a new advisory structure with shared membership between Ngāti Tūwharetoa, licence-holders, and the wider community (including the business sector) through a regulatory change | L | 3 | Gov | ü | ü |  | ü | ü | ü | ü | On hold | Highly unlikely under the current environment, would require the dis-establishment of TFAC
D1.Work with other organisations – power companies, district and regional councils, Ngāti Tūwharetoa, academic institutions, Crown Research Institutes, and Fish and Game – to develop a shared science and research strategy for Lake Taupō | L | 3 | Gov/Mgmt/Ops | ü | ü |  |  |  | ü | ü | On-going | Michel working with NIWA, Genesis Energy & NZ DOC Freshwater team. External research occurring with Advocates/TDC/DOC.Close relationship with WRC in supporting the interests of anglers as part of their ongoing flood and willow control work in the Tongariro and tauranga Taupo river. | Case by case
E3 (b). Support the establishment of learn to fish classes by clubs and/or commercial operators; and | L | 3 | Mgmt |  | ü | [5 empty] | On-going | TNTCS (Society) trialling fishing opportunities at TNTC. It has a very limited demand. DOC Fishery fully supports this aspiration, however uptake from the community has been limited. | case by case
E2 (a). Define and brand the full extent of the Taupō Sports Fishery; | L | 3 | Mgmt |  | ü | [5 empty] | Complete | The extend of the fishery is already well defined geographically. Branding the fishery is not a high priority goal, as the fishery already has a well established international profile. Maintaining this profile is a more important goal. Ongoing discussions with DGLT and where possible Tourism NZ will continue. | Branding not a priority for Fishery management at this stage. No intention to develop new brand.
D2. Consider the establishment of a collaborative structure to deliver the science and research priorities for Lake Taupō | L | 3 | Mgmt/Ops | ü | ü |  |  |  | ü | ü |  | Refer D1.
D7. Encourage greater ‘ownership’ and responsibility for fishery management among Ngāti Tūwharetoa and licence-holders generally, and in particular: | L | 4 | Mgmt | ü | ü |  | ü |  | ü | ü | Ongoing | New Manaaki Moana role will help in this regard, important symbolism of TMTB's comittment to the fishery
a. Re-engage a network of honorary rangers; | [10 empty] | Completed | Latest advice from NO Compliance team is DOC will not be using Honorary Rangers.
b. Establish a network of ‘ambassadors’ or ‘Friends of the Taupō Fishery.’ | [11 empty] | This is a very undefined goal, and not a priority at this stage
E1 (b). Develop a national licence option; | L | 4 | Mgmt/Gov | ü | ü | ü | ü | ü | ü | ü | On hold | DOC with F&G are taking part in a national fishing survey. Survey information will be used in determining whether this opportunity will be reassessed. However very unlikely to proceed as there is no demand from F&G or TMTB at this stage. All stakeholders see considerable issues with developing a workable solution for a national licence, given the differing seasons and business models involved.